## StrObv1
LINK BOARD 21 April 2016 Operational Plan 2016-2019 Report Paper 5.3
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Advocating for a sustainable Scotland | Scottish policy and its implement-ation are improved by expertise and evidence from the LINK network | LINK sharpens its focus to prioritise collaborative work on a smaller number of resourceable priorities, to have greater impact and influence. | Chair, MBs, Groups, CO, AO, MPAOs, SEO | Our priorities are selected to target relevant Government priorities such as jobs, fairness, wellbeing. KPIs 1.5, 1.9, 1.10. | Inputs consistently good, take up patchy. Meetings held by most, Planning 6th May. Land has done most original thinking re new strucutres: broad acceptance that the structures are an improvement; others still need to broaden their x-Group thinking. Social Justice discussions cut across all work areas, will confirm proposed plan by e May. Economics inputs to SJ work, held workshop with Marine on valuation issues. Various Groups contributed to Governance work via manifesto inputs. Some Subgroups amalgamated, Land Subgroups tasked with delivering priorities (Food& Farming, Wildlife, new Land Reform/Use/Scape Subgroup yet to meet). UFF Subgroup to decide which Group to feed through. NewC&E statement needs assessed by each group and used as framework for statements. Too soon in transition to judge impact.
|  | LINK strengthens its advocacy around those priorities, developing positive, solutions-focused approaches, communicating clearly about what we stand for | All players | Sustainable approaches, for Scotland and beyond, have more traction with decision makers. KPIs 1.1 to 1.6, 1.7, 1.8, | Good - improving. In some ways too soon to judge how transition affects our clarity of focus. Contact meetings with parties confirms their overriding interest in social justice. So framing SD in this context is going to matter. Economics sees hope in Green Party debate on just transition and environmental messages being presented in several manifestos (fracking, climate change, managing economy within environmental limits). Meetings held with all parties on manifestos. Economics - RACCE scrutinised some aspects rarely from economic viewpoint; EET considered topics but not from environmental point of view. Way to go in making the Nat Perf Fmwk what we want it to be. Slow movement on environmental courts (consultation published March). Greener strand in recent Fairness consultation evident; Minister received positively LINK's engagement in Fairness. Land - LR debate used many LINK messages and asks supported by MSPs x parties spectrum; some nods to joined up Govt in the Bill and in biodiversity strategies. Marine - Good, continued momentum re maintaining ambition on proper protection in MPAs from damaging fishing. Extent of x-compliance across departments poor though in marine terms. Planning - bit of mention of ERA by various spokespeople; pushing for planning to be more central across Depts than currently.
|  | We work with Government and other key decision-makers (through strategic dialogue, stakeholder forums, evidence, submissions, events) to help achieve sustainable development, collaborating closely as an effective way to exert influence; | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11 | Good constructive relations - some progress. Meeting with SG Environment e April on SG structures, how we can influence, where we sit in relation. Responses continue. LINK Groups very keen to see join-up of government's strategies and policies and pressing for that, eg Planning Group. LINK's 3 dedicated project officers make a difference to our ability to deliver, and funding beyond 2016 is not assured. Recent wins (marine) on MPAs.
|  | We will improve our local, national and international linkages to broaden the shared voice | Chair, trustees, MBs, Groups, staff mainly AO, CO, local links lead, MPAOs, SEO | Delegates on forums which are 'gaps'. Involved in obvious stakeholder groups. LOCAL matchmaking dbase well used. KPIs 1.6, 1,11. | Improving EEB will hold their 2017 event in Scotland coordinating with LINK, and that coincides with UK Presidency of EU. 2 LINK Groups supporting motions to IUCN Congress (wildlife crime, peatlands). J Hughes invited to May networking to discuss using IUCN more. Engagement in forums continues - new BIodiversity strcutures and engagement tbc. LINK Local database to be launched April 2016, developing slowly. Governance Group will start to plan strategy for local elections in 2017. Post-election there will be new forums to ensure we are involved in.
|  | We will advocate robustly for the environment in the public interest. | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11 | Good - room for improvement. Capacity related. Many areas waiting for Government 'response' or post-election action. Indications are that all parties have some env't components in manifestos as a result of eNGO advocacy. Marine campaign helped Gov to be robust. Planning ERA campaign broadening. Food Coalition established. Hustings ahead.

## KPI for 1.1 - 1.11
Outcome KPIs:
1.1 Extent to which LINK asks, messages and language are known to be used in parliamentary debate, FMQs, policy papers, and are reflected in the manifestos of the main political parties. Baseline at 2015-16 - Poor, Improving some areas
1.2 Level of M(S)P support for LINK network messages e.g. numbers of M(S)Ps attending LINK events; expressing commitment to environmental issues; Issues raised by LINK at meetings with decision-makers and opinion-formers taken forward by policy makers. Baseline is good at 2015-16
1.3 Level of Scottish Parliament scrutiny of delivery of environmental commitments e.g. delivery against SD Goals, targets in National Performance Framework, environmental principles informing decisions on development in Scotland, proposals in LINK’s ‘Governance Matters’ are met. Baseline - Poor, Improving some areas
1.4 Extent of Government cross-compliance across departments e.g. strategies and delivery are joined up (bio, land use, climate, economics, etc). Baseline: environmental measures in CAP/SRDP at 2015 are ‘not so good’
1.5 Extent to which Members and Groups in the network actively contribute to development of effective environmental policy.
Target: 66% of members participate in cycle of network meetings, 80% are involved in at least one Group. Baseline Good.
1.6 Connect more with other organisations and alliances. Target: eg other organisations are calling for similar/same things.
Output KPIs:
1.7 Size and mix of audiences at LINK events (from among decision-makers, opinion formers and wider civic Scotland)
1.8 Level and frequency of LINK (Board, Groups, Staff) access to decision-makers including MSPs/MPs/MEPs, Ministers, senior government officials and business leaders E.g. regular meetings with Environment Minister continue; LINK is involved in relevant forums. Target: at least 25 exchanges per year reflecting breadth of LINK agenda. Baseline Good/Very good
1.9 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from the Groups, in which at least 5 members are actively involved (per Group) and which meet at least 4 times a year. Baseline Very good
1.10 LINK Groups to plan their communications to various audiences highlighting the solutions focus and being clear about what they stand for.
1.11 Group plans to identify all relevant allies who share some of our agenda and the steps for joint work to increase impact. Eg., connect more with other organisations and alliances, look for opportunities to bring an environmental perspective to other agendas such as social justice.
Target: Groups and Subgroups identify annually appropriate linkages and follow these through. Baseline Room for improvement
SNH6: Provide a gateway for Government and RAFE partners among others to enable them to engage with the voluntary environment sector efficiently through LINK as the Intermediary.
SNH7: Provide evidence based feedback about how Scotland’s environmental objectives and obligations are faring through the various delivery mechanisms, via Ministerial and other meetings with officials, briefings and other LINK publications

## Str Obv 2
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Being a strong voice for Scotland's environment | The voluntary environmental community's contributions to evidence-based policy are stronger | Robust prioritisation, post-horizon scanning, is achieved, clear on member leads and support, so that LINK can do less, better | Chair, Trustees, MBs, Groups, CO, AO, AA, DO, MPAOs, SEO | LINK work programme delivers powerful advocacy around fewer key issues/campaigns. KPIs 2.3, 2.5, 2.9, | Good. Transition still bedding in and values being debated. Clear leadership for most areas. Need more support on Governance and SJ areas. Group meetings attendance is fairly good: Land VG, Marine VG, Social Justice VG, Planning G. Economics & Governance - small groups, both could do with more MB engagement.
|  | Policy messages are integrated both between LINK Groups and with member bodies' own work, to increase impact and resonate with national social and economic priorities | Group Conveners & identified communicators; MB Reps on Groups, Main Reps. | Member organisations' efforts are aligned, to achieve the above. | Good though hard to assess alignment with MBs' work. Some x-Group integration (Marine to Economics, Planning to Governance) though this needs active encouragement from above and support from those involved in the Groups. Marine - bottomed out MBs' variations on fisheries issues. Land - priorities arose from MBs' own work. Economics - eg., bio offsetting paper circulated. Governance - manifesto couched in broad SD terms for wide buy-in. SJ - too soon to judge. Planning - wide support for PD's equal rights of appeal campaign. Could perhaps do with some joint work on role of NPF, LUS, NMP and economic strategy. Planning group actively advocating for more join-up and more central role for these spatial documents in all government policy development to ensure better sustainability of wider policy development - this could benefit from joint work between Marine, Economics, Planning and Land Groups.
|  | Diversity of view is always explored, consensus accurately represented, and different approaches of members used to good effect, in developing positions | Groups, Conveners; Subgroups; MBs, Staff, Delegates | Positions, including differentiation, confidently expressed externally, so that shared 'asks' are clear, KPIs 2.3, 2.10, 3.5, 3.6 | Good - improving. Marine - good identification and exploring afoot. C&E - good process and strong sign-up, reframing of landscape statement in that context. Economics - circular economy, investment gap, and natural capital discussions amongst members. Governance - agreed common Scottish strategy for EU referendum despite MBs' differing stances across the UK. Direction of travel is to explore sores better before they fester - and this should be encouraged. Planning - good attendance and debate, info about responses shared.
|  | Internal agreed positions on our priorities are swiftly communicated across the network (among Groups Subgroups and Members) | Group Conveners & identified communicators between Groups & Subgroups; all MBs on Groups & Subgroups; Main Reps. Staff for bulletin & website. | Network and its members are aware of internal positioning, KPIs 3.7 | Communication of outputs is good via web, bulletin, social media. Extent to which they are noted by all who should see them is unclear.
|  | Connections are established with other civic sectors and coalitions, actively looking for opportunities to bring an envionmental perspective to issues of shared interest | Board, Groups/Conveners. Staff: AO, MPAOs, SEO mainly | Common ground developed with other civic sectors and coalitions and increases the size of the voice, for positive, timely action KPIs 1.11, 2.1 | Good. Marine & Economics linking well to other sectors. Governance also on legal strategy, lobbying. SJ discussions with others planned. Food Coalition estab with LINK help.
|  | Groups and relevant Subgroups develop their advocacy strategies at the outset, robust for the environment in the public interest. | Groups/Conveners, AO, MPAOs, SEO, CO and Board. | Advocacy strategies are monitored and adjusted to be fit for purpose and changing circumstances KPIs 2.7, 3.6 | Good, in hand.
|  | LINK consistently communicates key messages through website, social and other media to be relevant and resonate. | AO, DO, AOA, FOM, MPAOs, SEO, Interns | LINK website reflects current strategic priorities and positions in a way that engages our audiences. KPIs 1.10, 2.5. | Good and improving. Staff developing protocols for greater use of LINK website and social media. As well as actively using social media platforms more.
|  | Making best use of Hon Fells | Board, Groups, staff involved in facilitating the work. | How are Hon Offs involved in supporting Groups / LINK's work. | Improving 2 Fellows with active roles on groups. All invited to May network.
|  | Network skills in advocacy (comms, negotiation) are explicitly considered and provisioned appropriately when developing our advocacy strategies | Groups, Subgroups, AO, MPAOs, SEO, CO | advocacy strategies reference skills? Convenors report back on it? KPIs, 2.4, 3.6, | Variable - One Group has given it consideration. Others have not replied or see no problem.

## KPI for 2.1 - 2.10
Outcome KPIs:
2.1 LINK is contributing to relevant stakeholder groups/discussions to bring the environmental perspective. Baseline Good, but we need to extend our reach
2.2 Level of participation at and feedback from Group meetings, internal workshops and trainings arranged by LINK for members (on current issues, or skills needs). Target: 2 workshops or trainings arranged by staff per annum. (SNH target also) Baseline Good
2.3 Extent to which Groups influence direction of policy through good tactical planning. Targets: Groups are alive to the diversity of views within the network on the given issues. Advocacy strategies build on our strength in diversity, address practical issues of giving robust criticism (i.e. planning for the fallout), members and stakeholders value our ability to promote mature debate, inform policies and represent different voices.
2.4 Level of improvement in negotiating skills, based on Groups identifying their skills needs and these being addressed. Baseline: 3/13 TFs at 2015 felt things were good enough – so there is scope for improvement
2.5 LINK’s ability to add value as a collective voice. Baseline very good.
2.6 LINK Elected Trustee positions are mostly filled from within the network, annually. Baseline 8 of 9 at November 2015.
Output KPIs:
2.7 Number of networking events/opportunities and members participating in them (e.g. information exchange, policy workshops and training, negotiating skills). Target: 6 meetings/events; 2 workshops/trainings annually.
2.8 Number of opportunities afforded to meet and learn from other members. Target: minimum 8 (to include network level event and Groups and Subgroups in which hopefully every member is engaging at a minimum)
2.9 Identifying clear and resource-able network priorities with members from among the identified collective concerns. Target: that each annual planning meeting will identify these, and also agree areas which members will drop in order to resource the fresh priorities.
2.10 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from 5 Groups in which at least 5 members are actively involved (in each) and which meet at least 4 times a year
SNH1: Maintain a range of active Groups and Subgroups to be a forum for discussion and a platform for joint action, in which management of nature/environment forms a key element.
SNH2: Provide advocacy advice and coordinating support to Groups; horizon scanning of the broader socio-economic-environmental-political contexts at national and international levels; twice yearly political strategy reports for the Board and Network meetings; advice on advocacy strategy as Groups request it; ensuring regular reporting of progress on all topic areas; annual evaluation of Group and Subgroup activity to share learning across the network.
SNH3: Organise at least one training event (e.g. advocacy, media skills) for members annually, to improve members’ effectiveness in these areas
SNH4: Organise liaison meetings at strategic level with SNH and other SEARS/ENFOR partners (e.g. SEPA, FCS, National Parks, divisions within SG) a yearly basis; and with other key stakeholders in the policy community (e.g. land managers, faith groups, business interests, civic groups, academics, professions, trade unions, political parties, media, funding bodies) to establish relationships and build common cause for sustainability goals.
SNH8: Provide information to members through LINK’s membership and engagement with UK, EU and global networks to assist member bodies prepare for and react to changes in policy affecting Scotland’s environment.

## Str Obv 3
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Operating as an effective, efficient and accountable network | Operational capacity and processes meet network needs and goals | Annual planning process brings the network together, prioritises annual work programme to achieve strategic aims, resourcable and well led and focussed, which is reviewed at the two annual network meetings. | Chair, Trustees, Group Conveners, Subgroups, MBs, staff: CO, DO, AO, MPAOs, SEO | Annual work programme agreed informing agreed operational plan. KPIs 3.4, 3.5,3.6, 3.7, 3.9, 3.11, 3.13. | Good so far - new process. Prioritisation proposed at Nov 2015 aims to improve focus, leadership and impact. Reports collected in March for this evaluation. May and November 2016 meetings will take stock of whether the new approach improves our effectiveness.
|  | Intelligent horizon scanning ensures connection of LINK's annual priorities to relevant social and economic themes | Chair, AO, CO, MBs, Conveners, Governance Group | KPIs 3.13, also 1.6, 1.11, | Good to Very good. VG horizon scanning; are resource issues for LINK in following through sometimes, where member capacity is limited (eg economics, LINKLocal, EEB, how environment contributes to social justice).
|  | Group processes of agreeing priorities, integration, leadership (C & VC) are followed. Networking meetings and Board provide peer review. | Group Deputes, CO, DO | Plans reflect capacity, resources, strengths, integration and strategic goals, KPIs 3.3, 3.6, 3.7, 3.8,3.9 | Good so far. Integration and depute-ship to share the load, are areas to watch. Extent of member engagement in live work areas to be determined.
|  | Groups' communicate enough with other Groups, Subgroups and LINK centrally | Conveners, identified communicators, Subgroup Leaders; staff for website, emails, bulletin | Work plans and Members are clear about connection between Groups and Subgroups. KPIs 3.7 | Good? Relies on staff and those member reps who are involved in more than 1 area, for effective communications. Staff have been explicitly briefing players, but it is hard to know whether our emails are read, and whether the level of comms between groups is adequate for our ambition.
|  | Forward planning identifies relevant allies, audiences, forums and action |  | Plans supported by clear advocacy strategies. KPIs 3.11, | Good, esp re forums, audiences and action. There are capacity issues in building relations with allies, and the extent to which group members explicitly share this kind of work is unclear.
|  | Staff capacity to support Groups is sufficient. | Chair, AO, CO (and other allocated staff) and Network review discussions. | Staff work plans are clear about support to be provided to Work Programme. KPIs 3.10, 3.14 | Good currently. By end of 2016 could lose 3 project staff, which would significantly reduce support to and impact of 2 groups.
|  | Core events (Congress, SEW) support strategic priorities. | Groups, Trustees, DO, AO, AOA | Events address priorities, KPIs 2.9, 3.3, 3.9 | Good. Nov 2015 Congress discussions all relevant to our strategic aims. SEF 2016 good and doubled as Species Champions 'thank you'.
|  | Groups identify differences in organisations' views which could affect consensus (where that is a goal) and bottom out /problems are flagged to the centre for advice | Conveners, Deputes, Advocacy Staff, CO & Board | Differences in view which may matter are properly considered KPIs 3.5, 3.6, 3.7 | Good. Marine (detailed dscn re economics and mgt of fisheries in inshore MPAs and outwith offshore MPAs enabling clarity about what Group says/doesn't say), Economics (circular economy, bio offsetting, investment gap), Climate & Energy positining and Landscape statement. Groups are aware that they need to identify these potential areas.
|  | Members are given scope to present to network and talk with trustees about engagement and prospects | Chair and CO | Members know each others plans. Board understands membership KPIs 3.2. 3.4, 3.8, 3.9 3.11, 3.12, 3.13. | Good. Time is limited at network meetings. Bulletins offer scope to members though written word not as good as talking. Contact meetings useful conduit - re-offering shortly.
|  | Relevant audiences identified, allies with which to connect, forums requiring environmental voice | Chair and CO, Conveners for Group planning, Leaders for Subgroup planning, advocacy staff | .Number and nature of relevant audiences, allies and forums identified? KPIs 1.6, 1.10, 1.11, 2.1,. | Good, room for improvement. Identification of new audiences and new for a are at early stage in transition arrangements. We use James Curran to support FoES for Air Pollution Forum. Could usefully strategically assess post election, where (pllicy areas, other networks) we need to focus this effort.
|  | Evaluation is done for and by Board and Network meetings, informs on progress and pace, and plans are adjusted in the light of learning | Group Deputes, CO, DO, Trustees, Conveners | Evaluation complete, KPIs 3.11 | Good. Evaluation provided here. Network is evolving.
|  | Liaison meetings | Chair of meeting, staff organiser, MBs attending | Meetings are well prepared for and used strategically. KPI 1.8, 2.4 | Good. Ministerial and agency (at board level), other meetings via Groups - meetings are prpared for and are coherent, followed up. Impact variable and hard to judge.
|  | National organisations eligible for membership want to be part of the network and member bodies want to stay in LINK | Board (FSG) & staff monitor engagement levels & are proactive | 90% of members engaged in Work Programme, KPIs 3.1, 3.12 | Good. We hope new strategy will build cohesion and ex-members will come back. Some new interest being shown from smaller orgs.
|  | Board ensures skills, diversity and CPD opportunities | Trustees (Subgroup), MBs, CO facilitates | Board membership is appropriate. KPIs 2.6, 3.4, 3.12 | Good. Succession planning ongoing. Induction for Lucy Graham January.
|  | New member organisations, fresh Reps, new Trustees and incoming Staff will be given very good inductions, with follow-up in the first eighteen months | CO, DO, AO, and other staff and trustees/deputes as needed | Members understand how LINK operates and how to engage. KPI 3.4 | Room for improvement. In some cases new member Reps are not always responding to induction offers. Structured follow-up needs to be planned.
|  | LINK policies on employment follow good practice and ESG plays active role in monitoring | Board, CO, FOM | Confident, supported staff supports delivery of strategy, KPI 3.14 | Good.
|  | LINK policies for staff, Groups and delegates are followed | Board, CO, FOM, anyone organising events | Ops carried out in line with SD values, KPIs 3.4 | Good-ish. Few problems identified, except with 1 member around wording of LINK strategy. Has been discussion around the sign-off arrrangements for Subgroups and Forums having to be via Groups.
|  | LINK funding strategy looks 5 years ahead | Board (FSG), CO, DO, FOM | LINK's stability for 3 years ahead ensured, KPIs 3.10. | Good, scope for improvement. We look that far ahead with varying degrees of certainty. Core has limited authority over Groups in terms of fundraising preferences.
|  | Funding is a blend of membership (at least 60% of Essential Costs) and external, with public sector meeting <25% total income | DO, CO, FOM. Board FSG | Independence of voice & resourceability of strategy ensured, KPIs 3.10, 3.14 | M'ship accounts for 57% Essential Costs. Public sector future unknown. Trust component unknown post 2016.
|  | Active Board meets at least quarterly to assess progress | Trustees, CO, DO, AO, FOM | Delivery of strategy is monitored KPI many relate | Good. Meets regularly, is quorate.
|  | LINK's administrative functions are kept under review | CO, FOM, AOA, DO | Admin supports strategy and effective running of organisation, KPIs 3.14 | Good. 2015 review of staffing functions made various adjustments, and changes in 3 of 5 posts gave opportunity for some of these.

## KPI for 3.1 - 3.14
Outcome KPIs:
3.1 Number of citizen-led, national level eNGOs that are LINK members (i.e. leaving/joining/sustaining membership annually)
3.2 Extent to which members are aware of LINK priorities and opportunities to engage with these. Baseline: members are offered 1:1 meeting with a trustee, annually.
3.3 Process for setting and agreeing priorities is implemented and reviewed. Targets: There are no more than 5-6 priority themes (Groups) at a time through which all Subgroups operate.
3.4 New Members, Reps, Trustees, Staff receive very good induction and follow-up within eighteen months – this informs member on how /where they can engage. Baseline: very good inductions at 2015; more time needed in follow-up
3.5 Extent to which the network is live to the diversity of member interests and views. Target: Strategic Planning, Groups, and Board, encourage full membership engagement in policy work all members to be aware of the issues being addressed and the direction of any likely consensus. Baseline: Structures allow members’ views to come through (eg Board’s 1-1 contact with members, Groups and Subgroups in which members can engage)
3.6 Groups are explicit about strengths and diversity, and reflect these in their plans and tactics. Baseline at 2015 Poor
3.7 Extent to which LINK messages are harmonised, avoiding contradiction or duplication, collaborating when needed. Targets: Groups are consistently represented at Network meetings. Groups pursue strategic LINK priorities. Group-to-Group communications flag intents and integration needs.
3.8. Extent to which Subgroups and Groups are aware of the spread of members in the network and are content that all relevant members are participating and feel their goals are met. Baseline: Very good under TF structure at 2015. (May need to assess this annually with members)
3.9 Annual network Work Programme reflects considered discussion and priorities and engages at least 75% of members in its delivery. Baseline: Very good under TF structure
3.10 There is a breadth and blend of financial support for LINK from a range of sources to sustain LINK’s independence and maintain our right and responsibility to be a strong voice for the environment.
Targets:
· Membership funding underpins 60% of essential services
· Government/public sector funding for 2015/16 represents no more than 25% of total income
· Business support for LINK (as event/initiative sponsors or as Business Supporters) represents 7% of total LINK income by 2016/17
Also:
2.6 LINK Elected Trustee positions are mainly filled from within the network annually.
Output KPIs:
3.11 An annual Work Programme of the network’s intended work is prepared with Member, Group, Subgroup and Board input, and is subject to twice yearly review and evaluation. Review should include the extent to which the plans are resourced and members’ have made commitment to implementing them.
3.12 There is proactive engagement by 90% of members in some area of LINK policy or governance annually. Baseline: 90% at 2015
3.13 Annual strategic planning process gives members a platform to present on their directions, allows the network to collectively sign off on priorities for joint work ahead, with up-to-date intelligence about goals and contexts, and identifies leads and those responsible for integration. Baseline: Check at May 2016
3.14 Board (with FSG and ESG) reviews whether the organisation is stretched, working at (or over) capacity – ie whether the money, time, personnel, membership, skills and knowledge available are fit for the priorities. Includes at a minimum: staff support to every Group for arranging, attending and minuting up to 4 meetings per year; fundraising time is available for priorities; processes and structures encourage collective work under the LINK umbrella rather than outside that umbrella. Baseline: tbc end 2016.
SNH5: Organising 3 network meetings per year at which stewardship of Scotland’s environment is discussed in the round by LINK members and Groups, plans are adjusted as events develop, further workshops are organised as needed, lessons are shared and new opportunities explored.