## StrObv1
LINK BOARD APRIL 2017 Operational Plan 2016-2019 Report Paper 3.1
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Advocating for a sustainable Scotland | Scottish policy and its implement-ation are improved by expertise and evidence from the LINK network | LINK sharpens its focus to prioritise collaborative work on a smaller number of resourceable priorities, to have greater impact and influence. | Chair, MBs, Groups, CO, AO, MPAOs, SEO | Our priorities are selected to target relevant Government priorities such as jobs, fairness, wellbeing. KPIs 1.5, 1.9, 1.10. Baseline Oct 2016: Inputs very good, take up improving | Inputs very good, take up improving: Land: very good, members of ECCLR & REC Cttees, both Cab Secs & many Species Champions can be evidenced using messages & language from LINK Briefings. Marine: Refs to marine species & member bodies in Species Champs debate in Parl by 2 MSPs. MS Fisheries team remain committed to Inshore Fisheries Bill in SNP Manifesto. Economics: no measurable effect at present. EJ&FW Ctte raised funding in their response to draft Climate Plan, poss influenced by LINK messaging. Governance: LINK is a key interlocutor with academic work on Brexit & contacts in Scottish Think Tank on Europe. As such messages going direct to Gov as well as through academic networks (SULNE). LINK was involved with civil society report Rights at Risk, linking env with human rights, mentioned by MSPs in debate. Planning: White Paper reflects inputs in its language, esp wrt planning & land use, though right of appeal rejected. 90 MSPs are Species Champions.
|  | LINK strengthens its advocacy around those priorities, developing positive, solutions-focused approaches, communicating clearly about what we stand for. | All players | Sustainable approaches, for Scotland and beyond, have more traction with decision makers. KPIs 1.1 to 1.6, 1.7, 1.8, Baseline Oct 16: Good- steadily improving | Good: Land; x party support for info and opps offered by LINK. Adequate scrutiny by Parl tho env seldom top priority, albeit examples like deer mgt receiving dedicated attention. X-compliance better but still need to keep making the case. Economics: MSPs and MP at Nov conf supported LINK message; Marine: MSP pursued blue carbon asks in ECCLR scrutiny of RPP3. Same MSP requested briefing for biodiversity debate. Multiple motions by MSPs in support of MG member activities; ECCLR took evidence on Bio 2020 targets, including from MCS covering LINK points; ECCLR took of LINK evidence on omission of blue carbon in CC Adaptation Programme. Evidence givento cttee on fisheries. Governance: good level of engagement beyond ECCLR, incl with REC - important given implications of new division of responsibilities in Gov and Parl. Planning: support fairly good at mo among opposition parties. We could make more effort to message other MSPs. Pl. issues not yet at scrutiny stage. on X compliance, some good words in the White Paper which we will need to push to have implemented.
|  | We work with Government and other key decision-makers (through strategic dialogue, stakeholder forums, evidence, submissions, events) to help achieve sustainable development, collaborating closely as an effective way to exert influence; | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11 Basline Oct 16: Good and improving | Good: Land: good level of access with excellent support from AO and members' parly staff, arranging meetings at all levels, roundly appreciated by all; Economics: Not sought political liaison in period, good access to Performance Unit, including participation in the Nov conf, supported by RSA & David Hume Institute. Dev'd link with 2020 business group, & 2 businesses through the conf, continued good relations with SCDI - came to Congress. Marine: good engagement with MS and SNH staff; tensions with MS over fisheries mgt being well managed. Access to Cab Secs seems difficult on marine issues; Governance: frequent access from officials to Cab Secs on GG issues; successful legal strategy conference with legal community. Various groups and subgroups have given evidence in the period. Continue involvement in many forums; some concern about biodiversity delivery groups, only 2 NGO reps involved in March stakeholder meeting. Interest from SNH and others on NEN. Significant advocacy afoot on deer. AO covers all party conference at least annually. Congress included good represention from other sectors, and agencies. SEW well supported by MSPs and others. 90 Species Champions includes some ministers and Cab Secs. Gov and agencies signalling support for EEB conf.
|  | We will improve our local, national and international linkages to broaden the shared voice | Chair, trustees, MBs, Groups, staff mainly AO, CO, local links lead, MPAOs, SEO | Delegates on forums which are 'gaps'. Involved in obvious stakeholder groups. LOCAL matchmaking dbase well used. KPIs 1.6, 1,11. Baseline Oct 16: Good | Good: Developing programme with EEB for 2017 international conference. Congress looked at opps for international collaboration outwith EU; Our engagement with IUCN minimal during period. Through GG and ELUK, proactively engaging with Greener UK on NGO Brexit positioning. Continue to promote LINK Local as capacity allows. GG members & LINK will message through various media in advance of May local elections. AO continues to participate in relevant SCVO initiatives.
|  | We will advocate robustly for the environment in the public interest. | Chair, trustees, Groups, Sub-Groups, MBs, delegates, staff: AO, CO, DO, MPAOs, SEO | LINK keeps Govt to account on obligations, and public clamour for change grows. KPIs 1.7, 1.8,1.11. Baseline Oct 16: Very Good | Very Good: Groups report that extent of members willingess to be robust varies. Marine: advocacy tempered on fisheries in light of F Ewing appointment, with a developed campaign pulled. On Planning response, which had a very short turnaround time, one member felt it should have been stronger; Earlier strength of advocacy on wildlife crime is bearing fruit, as recent Justice cttee inquiry showed. Potential to use our 90 Species Champions strategically across the policy spectrum.

## KPI for 1.1 - 1.11
Outcome KPIs:
1.1 Extent to which LINK asks, messages and language are known to be used in parliamentary debate, FMQs, policy papers, and are reflected in the manifestos of the main political parties. Baseline at 2015-16 - Poor, Improving some areas
1.2 Level of M(S)P support for LINK network messages e.g. numbers of M(S)Ps attending LINK events; expressing commitment to environmental issues; Issues raised by LINK at meetings with decision-makers and opinion-formers taken forward by policy makers. Baseline is good at 2015-16
1.3 Level of Scottish Parliament scrutiny of delivery of environmental commitments e.g. delivery against SD Goals, targets in National Performance Framework, environmental principles informing decisions on development in Scotland, proposals in LINK’s ‘Governance Matters’ are met. Baseline - Poor, Improving some areas
1.4 Extent of Government cross-compliance across departments e.g. strategies and delivery are joined up (bio, land use, climate, economics, etc). Baseline: environmental measures in CAP/SRDP at 2015 are ‘not so good’
1.5 Extent to which Members and Groups in the network actively contribute to development of effective environmental policy.
Target: 66% of members participate in cycle of network meetings, 80% are involved in at least one Group. Baseline Good.
1.6 Connect more with other organisations and alliances. Target: eg other organisations are calling for similar/same things.
Output KPIs:
1.7 Size and mix of audiences at LINK events (from among decision-makers, opinion formers and wider civic Scotland)
1.8 Level and frequency of LINK (Board, Groups, Staff) access to decision-makers including MSPs/MPs/MEPs, Ministers, senior government officials and business leaders E.g. regular meetings with Environment Minister continue; LINK is involved in relevant forums. Target: at least 25 exchanges per year reflecting breadth of LINK agenda. Baseline Good/Very good
1.9 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from the Groups, in which at least 5 members are actively involved (per Group) and which meet at least 4 times a year. Baseline Very good
1.10 LINK Groups to plan their communications to various audiences highlighting the solutions focus and being clear about what they stand for.
1.11 Group plans to identify all relevant allies who share some of our agenda and the steps for joint work to increase impact. Eg., connect more with other organisations and alliances, look for opportunities to bring an environmental perspective to other agendas such as social justice.
Target: Groups and Subgroups identify annually appropriate linkages and follow these through. Baseline Room for improvement
SNH6: Provide a gateway for Government and RAFE partners among others to enable them to engage with the voluntary environment sector efficiently through LINK as the Intermediary.
SNH7: Provide evidence based feedback about how Scotland’s environmental objectives and obligations are faring through the various delivery mechanisms, via Ministerial and other meetings with officials, briefings and other LINK publications

## Str Obv 2
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Being a strong voice for Scotland's environment | The voluntary environmental community's contributions to evidence-based policy are stronger | Robust prioritisation, post-horizon scanning, is achieved, clear on member leads and support, so that LINK can do less, better | Chair, Trustees, MBs, Groups, CO, AO, AOA, DO, MPAOs, SEO | LINK work programme delivers powerful advocacy around fewer key issues/campaigns. KPIs 2.3, 2.5, 2.9, Baseline Oct 16: Good, Progress steady | Good, Progress continues. We revisited 6 priorities and decided that Social Justice could not be sustained by a Group, so adjusted tack to cross cutting comms. Climate was agreed as short term priority in lead up to Bill. Reduction in project funding will reduce Groups capacities. Leadership of groups is good - it is the membership commitment that in some cases is the problem.
|  | Policy messages are integrated both between LINK Groups and with member bodies' own work, to increase impact and resonate with national social and economic priorities. | Group Conveners & identified communicators; MB Reps on Groups, Main Reps. | Member organisations' efforts are aligned, to achieve the above. Baseline Oct 16: Good progress and improving. | Good progress and improving. Land: membership crosses well with Planning & Governance, keeping messages harmonised. Marine: close contact with Planning, Governance, Wildlife Subgroup. Economics; relevance to other groups considered. Working well across our land-focussed groupings. Level of member commitment and engagement would indicate LINK work underpins members' own goals. Good comms between Groups through both the staff pariticpation and degree of member overlap. Social justice effort drew on many members and groups. No problems identified.
|  | Diversity of view is always explored, consensus accurately represented, and different approaches of members used to good effect, in developing positions | Groups, Conveners; Subgroups; MBs, Staff, Delegates | Positions, including differentiation, confidently expressed externally, so that shared 'asks' are clear, KPIs 2.3, 2.10, 3.5, 3.6 Baseline Oct 16 Good-improvement continues | Good and improving. Land: planned work tends to focus on strengths. diversity is dealt with as it arises. Economics: this could be improved. members own areas of work generally seen as separate to the collective work. In absence of a SEPO, this may reduce the sense of collectiveness. On natural capital consensus, are focusing on the areas of agreement rather than dispute. Marine: focussed on its core work of Marine Act implementation, and could do more on areas eg aquaculture, going forward. Planning: very good mix of expertise, technical knowledge and community focus within membership. Will need to focus more on using this diversity within advocacy strategy towards end 2017.
|  | Internal agreed positions on our priorities are swiftly communicated across the network (among Groups Subgroups and Members) | Group Conveners & identified communicators between Groups & Subgroups; all MBs on Groups & Subgroups; Main Reps. Staff for bulletin & website. | Network and its members are aware of internal positioning, KPIs 3.7. Baseline Oct 16: Comms of outputs good. | Good: Communication of outputs continues to be good via websites, bulletin, social media, though we know they are not read and digested by all.
|  | Connections are established with other civic sectors and coalitions, actively looking for opportunities to bring an envionmental perspective to issues of shared interest | Board, Groups/Conveners. Staff: AO, MPAOs, SEO mainly | Common ground developed with other civic sectors and coalitions and increases the size of the voice, for positive, timely action KPIs 1.11, 2.1 Baseline Oct 16 : Good and improving | Good and improving: In this respect most groups continue to be proactive.
|  | Groups and relevant Subgroups develop their advocacy strategies at the outset, robust for the environment in the public interest. | Groups/Conveners, AO, MPAOs, SEO, CO and Board. | Advocacy strategies are monitored and adjusted to be fit for purpose and changing circumstances KPIs 2.7, 3.6 Baseline Oct 16 Good, and improving | Good: Development of advocacy strategies tends to be on a needs basis, for some it is more implicit than explicit.
|  | LINK consistently communicates key messages through website, social and other media to be relevant and resonate. | AO, DO, AOA, FOM, MPAOs, SEO, Interns | LINK website reflects current strategic priorities and positions in a way that engages our audiences. KPIs 1.10, 2.5.: Baseline Oct 16: Good and improving | Good, This continues with no particular developments over this period. .
|  | Making best use of Hon Fells | Board, Groups, staff involved in facilitating the work. | How are Hon Offs involved in supporting Groups / LINK's work. Baseline Oct 16, Good - Improving | Good Explicit effort Spring 2017 to engage Fellows in Network meeting, which will inform where they can engage. Several already are very active - Air Quality and Legal Strategy.
|  | Network skills in advocacy (comms, negotiation) are explicitly considered and provisioned appropriately when developing our advocacy strategies | Groups, Subgroups, AO, MPAOs, SEO, CO | advocacy strategies reference skills? Convenors report back on it? KPIs, 2.4, 3.6, Baseline October 16: Improving | Improving: AO has helped some groups with their advoacy strategies. Several are confident with their skills level. Some have not responded to this question.

## KPI for 2.1 - 2.10
Outcome KPIs:
2.1 LINK is contributing to relevant stakeholder groups/discussions to bring the environmental perspective. Baseline Good, but we need to extend our reach
2.2 Level of participation at and feedback from Group meetings, internal workshops and trainings arranged by LINK for members (on current issues, or skills needs). Target: 2 workshops or trainings arranged by staff per annum. (SNH target also) Baseline Good
2.3 Extent to which Groups influence direction of policy through good tactical planning. Targets: Groups are alive to the diversity of views within the network on the given issues. Advocacy strategies build on our strength in diversity, address practical issues of giving robust criticism (i.e. planning for the fallout), members and stakeholders value our ability to promote mature debate, inform policies and represent different voices.
2.4 Level of improvement in negotiating skills, based on Groups identifying their skills needs and these being addressed. Baseline: 3/13 TFs at 2015 felt things were good enough – so there is scope for improvement
2.5 LINK’s ability to add value as a collective voice. Baseline very good.
2.6 LINK Elected Trustee positions are mostly filled from within the network, annually. Baseline 8 of 9 at November 2015.
Output KPIs:
2.7 Number of networking events/opportunities and members participating in them (e.g. information exchange, policy workshops and training, negotiating skills). Target: 6 meetings/events; 2 workshops/trainings annually.
2.8 Number of opportunities afforded to meet and learn from other members. Target: minimum 8 (to include network level event and Groups and Subgroups in which hopefully every member is engaging at a minimum)
2.9 Identifying clear and resource-able network priorities with members from among the identified collective concerns. Target: that each annual planning meeting will identify these, and also agree areas which members will drop in order to resource the fresh priorities.
2.10 Number of collective position statements (including briefings, publications) that are published by LINK to decision-makers and civic society on key priorities reflecting the range and diversity of interests across the LINK network. Target: At least 15 per year, drawn from 5 Groups in which at least 5 members are actively involved (in each) and which meet at least 4 times a year
SNH1: Maintain a range of active Groups and Subgroups to be a forum for discussion and a platform for joint action, in which management of nature/environment forms a key element.
SNH2: Provide advocacy advice and coordinating support to Groups; horizon scanning of the broader socio-economic-environmental-political contexts at national and international levels; twice yearly political strategy reports for the Board and Network meetings; advice on advocacy strategy as Groups request it; ensuring regular reporting of progress on all topic areas; annual evaluation of Group and Subgroup activity to share learning across the network.
SNH3: Organise at least one training event (e.g. advocacy, media skills) for members annually, to improve members’ effectiveness in these areas
SNH4: Organise liaison meetings at strategic level with SNH and other SEARS/ENFOR partners (e.g. SEPA, FCS, National Parks, divisions within SG) a yearly basis; and with other key stakeholders in the policy community (e.g. land managers, faith groups, business interests, civic groups, academics, professions, trade unions, political parties, media, funding bodies) to establish relationships and build common cause for sustainability goals.
SNH8: Provide information to members through LINK’s membership and engagement with UK, EU and global networks to assist member bodies prepare for and react to changes in policy affecting Scotland’s environment.

## Str Obv 3
Strategic Objective | Outcomes sought in pursuit of objective | Action to be taken to achieve that outcome | Responsible players | Relevant KPIs and baseline or target | Progress/Status
Operating as an effective, efficient and accountable network | Operational capacity and processes meet network needs and goals | Annual planning process brings the network together, prioritises annual work programme to achieve strategic aims, resourcable and well led and focussed, which is reviewed at the two annual network meetings. | Chair, Trustees, Group Conveners, Subgroups, MBs, staff: CO, DO, AO, MPAOs, SEO | Annual work programme agreed informing agreed operational plan. KPIs 3.4, 3.5,3.6, 3.7, 3.9, 3.11, 3.13. Baseline Oct 16: Good, room for improvement. | Good, needs tight management: Good strategic planning discussion added some further issues to relevant plans, and identified x group work needs. The increasing pull on AO time from Groups and Subgroups was flagged there, and is being monitored. Project funding uncertainty continues, Economics will lose SEPO in May. Hilltracks succeeded in its fundraising for its monitoring needs. Board has agreed £5k spend on climate work coordination. Brexit work taking a lot of time.
|  | Intelligent horizon scanning ensures connection of LINK's annual priorities to relevant social and economic themes | Chair, AO, CO, MBs, Conveners, Governance Group | KPIs 3.13, also 1.6, 1.11, Baseline Oct 16: Good to Very Good | Good to Very good. VG horizon scanning at Strategic Planning meeting. Flagged the resource deficit to tackle SJ as a priority, agreeing to address in comms across work areas, much falls to AO here. Without SEPO, Economics work will be reduced.
|  | Group processes of agreeing priorities, integration, leadership (C & VC) are followed. Networking meetings and Board provide peer review. | Group Deputes, CO, DO | Plans reflect capacity, resources, strengths, integration and strategic goals, KPIs 3.3, 3.6, 3.7, 3.8,3.9. Baseline Oct 16: Good, issues remain. | Good, issues remain. Groups and Subgroups know what they want to do, are assessing capacity, clear on limitations. If funding for Species Champions does not materialise, core staff can't fully compensate. Board in Jan recognised the reliance on a few key individuals in many groups/subgroups and will air at May network. Integration happens due to cross-over of people on different groups and to an extent via staff. Network meetings function includes peer review.
|  | Groups communicate enough with other Groups, Subgroups and LINK centrally | Conveners, identified communicators, Subgroup Leaders; staff for website, emails, bulletin | Work plans and Members are clear about connection between Groups and Subgroups. KPIs 3.7. Baseline Oct 16: May be improving | Good; kept on the agenda for all Group meetings and relies mostly on staff / member reps who are involved in more than 1 area, for effective communications.
|  | Forward planning identifies relevant allies, audiences, forums and action |  | Plans supported by clear advocacy strategies. KPIs 3.11, Baseline Oct 16: Good. | Good - we aspire to improve! Not all Groups have explicit advocacy strategies yet. Some are very advanced in theirs. Strategic Planning thoroughly explored allies, though capacity to follow up some aspirations, eg Health messaging with other interests id'ed at Congress, is limited. Can blockages be overcome?
|  | Staff capacity to support Groups is sufficient. | Chair, AO, CO (and other allocated staff) and Network review discussions. | Staff work plans are clear about support to be provided to Work Programme. KPIs 3.10, 3.14. Baseline Oct 16: Good - problems ahead! | Good - provided we manage tightly. Board has agreed £5k for Climate coordiation. Brexit (Governance), and other priorities account for AO time. Species Champions support gone, gap opening there, with Economics and potentially with Marine . Staff workload remains consistently busy, particularly for AO.
|  | Core events (Congress, SEW) support strategic priorities. | Groups, Trustees, DO, AO, AOA | Events address priorities, KPIs 2.9, 3.3, 3.9. Basleine Oct 16: Good | Good: Congress addressed Brexit and links with social and economic agendas. SEW 2017 made new contacts with the Arts sector. Planning Group event held. Members made good use of seminar slots, with much coordination time from AOA. SEW review scheduled.
|  | Groups identify differences in organisations' views which could affect consensus (where that is a goal) and bottom out; problems are flagged to the centre for advice | Conveners, Deputes, Advocacy Staff, CO & Board | Differences in view which may matter are properly considered KPIs 3.5, 3.6, 3.7. Baseline Oct 16: Good | Good: Land - not much divergence within the Group but subtle variations addressed case by case. Economics: live to diversity, developing positions. pleased that WWFS attended latest meeting; membership remains small. see potential for others to engage. Governance: live to diversity and breadth of views, and issues where such diversity is more likely; Planning; working well, no problems. Wildlife Crime now has SWT back as an observer, which is improving. NTS remains outside. Marine has candid debate. Now has Aquaculture Subgroup. Deer Subgroup position not fully supported by NTS?
|  | Members are given scope to present to network and talk with trustees about engagement and prospects | Chair and CO | Members know each others plans. Board understands membership KPIs 3.2. 3.4, 3.8, 3.9 3.11, 3.12, 3.13. Baseline Oct 16: Good | Good: this tends to happen at Group and Subgroup level rather than at network meetings with busy agendas. Bulletins offer scope, if read. Contact meetings continue to be offered. We should keep an eye here for organisations not closely involved in Groups.
|  | Relevant audiences identified, allies with which to connect, forums requiring environmental voice | Chair and CO, Conveners for Group planning, Leaders for Subgroup planning, advocacy staff | .Number and nature of relevant audiences, allies and forums identified? KPIs 1.6, 1.10, 1.11, 2.1,. Baseline Oct 16: Good | Good: Process is being followed
|  | Evaluation is done for and by Board and Network meetings, informs on progress and pace, and plans are adjusted in the light of learning | Group Deputes, CO, DO, Trustees, Conveners | Evaluation complete, KPIs 3.11; Baseline April 16: Good | Good: Process is being pursued. Extent to which lesson learned and plans adjusted difficult for staff to know - Strategic planning to explore.
|  | Liaison meetings | Chair of meeting, staff organiser, MBs attending | Meetings are well prepared for and used strategically. KPI 1.8, 2.4 Baseline Oct 16: good | Good: meetings held with R. Cunningham on EEB conference & marine; CNPA with members, with SEPA Chair, all have been well prepared for, useful.
|  | National organisations eligible for membership want to be part of the network and member bodies want to stay in LINK | Board (FSG) & staff monitor engagement levels & are proactive | 90% of members engaged in Work Programme, KPIs 3.1, 3.12 Baseline Oct 16: Good. | Good: 91% engaged in work programme (SCAPE, Scot Geodiversity Forum, WWT not engaged in work programme currently). New members Scottish Geodiversity Forum, 2 pipeline applications (SWBG, and S&TCS). Question over JMT's involvement in Deer to be raised with new CEO, after June. Feeling is that consideration of rejoining LINK may need to wait for new JMT chair. Keeping eye on situation and exploring possibilities (Rewilding Britain, Salmon & Trout Conservation Scotland).
|  | Board ensures skills, diversity and CPD opportunities | Trustees (Subgroup), MBs, CO facilitates | Board membership is appropriate. KPIs 2.6, 3.4, 3.12. Baseline Oct 16: Good | Good: Skills register on Board agenda. Succession planning ongoing.
|  | New member organisations, fresh Reps, new Trustees and incoming Staff will be given very good inductions, with follow-up in the first eighteen months | CO, DO, AO, and other staff and trustees/deputes as needed | Members understand how LINK operates and how to engage. KPI 3.4 Baseline Oct 16: Improving | Good: Ongoing for members, new staff, new conveners/leaders, and any that ask.
|  | LINK policies on employment follow good practice and ESG plays active role in monitoring | Board, CO, FOM | Confident, supported staff supports delivery of strategy, KPI 3.14 Baseline Oct 16: Good | Good: Handbook is up to date, FOM will check redundancy situation. Pension provision reviewed, LINK is auto-enrolled with new provider Peoples Pension, staff being advised to make relevant decisions. Marine Steering Group recently managing complex contractual situation as funding fluctuates and mat cover. ESG consulted on and approved temporary additional spend on policy support for a priority (Climate).
|  | LINK policies for staff, Groups and delegates are followed | Board, CO, FOM, anyone organising events | Ops carried out in line with SD values, KPIs 3.4 Baseline Oct 16: Good | Good: These are followed. Current review of Governance may flag gaps. One issue flagged is JMT's continued involvement in the Deer Subgroup, contravening protocols.
|  | LINK funding strategy looks 5 years ahead | Board (FSG), CO, DO, FOM | LINK's stability for 3 years ahead ensured, KPIs 3.10. Baseline Oct. 16: Good. | Good: Fundraising is tougher. Longer term scenario revised, FSG delegated to advise.
|  | Funding is a blend of membership (at least 60% of Essential Costs) and external, with public sector meeting <25% total income | DO, CO, FOM. Board FSG | Independence of voice & resourceability of strategy ensured, KPIs 3.10, 3.14 Baseline at Oct 16 Amber Warning: M'ship accounted for 57% of ES. | Good, but Amber warning continues: M'ship accounts for 57.2% of Essential Costs. Public sector grant staying level (verbal assurance). Financial item on the agenda pertains.
|  | Active Board meets at least quarterly to assess progress | Trustees, CO, DO, AO, FOM | Delivery of strategy is monitored KPI many relate Baseline Oct 16: Good | Good. Meets regularly, quorate. One coopted trustee stepped down at AGM, no elected vacancies. Need to encourage at least one nomination for December AGM.
|  | LINK's administrative functions are kept under review | CO, FOM, AOA, DO | Admin supports strategy and effective running of organisation, KPIs 3.14 Baseline Oct 16: Good | Very Good: Operating well with current staff mix of skills. Reviewing our financial future and capacity at spring 2017.

## KPI for 3.1 - 3.14
Outcome KPIs:
3.1 Number of citizen-led, national level eNGOs that are LINK members (i.e. leaving/joining/sustaining membership annually)
3.2 Extent to which members are aware of LINK priorities and opportunities to engage with these. Baseline: members are offered 1:1 meeting with a trustee, annually.
3.3 Process for setting and agreeing priorities is implemented and reviewed. Targets: There are no more than 5-6 priority themes (Groups) at a time through which all Subgroups operate.
3.4 New Members, Reps, Trustees, Staff receive very good induction and follow-up within eighteen months – this informs member on how /where they can engage. Baseline: very good inductions at 2015; more time needed in follow-up
3.5 Extent to which the network is live to the diversity of member interests and views. Target: Strategic Planning, Groups, and Board, encourage full membership engagement in policy work all members to be aware of the issues being addressed and the direction of any likely consensus. Baseline: Structures allow members’ views to come through (eg Board’s 1-1 contact with members, Groups and Subgroups in which members can engage)
3.6 Groups are explicit about strengths and diversity, and reflect these in their plans and tactics. Baseline at 2015 Poor
3.7 Extent to which LINK messages are harmonised, avoiding contradiction or duplication, collaborating when needed. Targets: Groups are consistently represented at Network meetings. Groups pursue strategic LINK priorities. Group-to-Group communications flag intents and integration needs.
3.8. Extent to which Subgroups and Groups are aware of the spread of members in the network and are content that all relevant members are participating and feel their goals are met. Baseline: Very good under TF structure at 2015. (May need to assess this annually with members)
3.9 Annual network Work Programme reflects considered discussion and priorities and engages at least 75% of members in its delivery. Baseline: Very good under TF structure
3.10 There is a breadth and blend of financial support for LINK from a range of sources to sustain LINK’s independence and maintain our right and responsibility to be a strong voice for the environment.
Targets:
· Membership funding underpins 60% of essential services
· Government/public sector funding for 2015/16 represents no more than 25% of total income
· Business support for LINK (as event/initiative sponsors or as Business Supporters) represents 7% of total LINK income by 2016/17
Also:
2.6 LINK Elected Trustee positions are mainly filled from within the network annually.
Output KPIs:
3.11 An annual Work Programme of the network’s intended work is prepared with Member, Group, Subgroup and Board input, and is subject to twice yearly review and evaluation. Review should include the extent to which the plans are resourced and members’ have made commitment to implementing them.
3.12 There is proactive engagement by 90% of members in some area of LINK policy or governance annually. Baseline: 90% at 2015
3.13 Annual strategic planning process gives members a platform to present on their directions, allows the network to collectively sign off on priorities for joint work ahead, with up-to-date intelligence about goals and contexts, and identifies leads and those responsible for integration. Baseline: Check at May 2016
3.14 Board (with FSG and ESG) reviews whether the organisation is stretched, working at (or over) capacity – ie whether the money, time, personnel, membership, skills and knowledge available are fit for the priorities. Includes at a minimum: staff support to every Group for arranging, attending and minuting up to 4 meetings per year; fundraising time is available for priorities; processes and structures encourage collective work under the LINK umbrella rather than outside that umbrella. Baseline: tbc end 2016.
SNH5: Organising 3 network meetings per year at which stewardship of Scotland’s environment is discussed in the round by LINK members and Groups, plans are adjusted as events develop, further workshops are organised as needed, lessons are shared and new opportunities explored.