This Work Programme sits below LINK’s Strategy 2016-19 and Operational Plan.

The Strategy sets out in broad terms what the Network aims to do.

The Operational Plan sets out what is required to achieve our strategic objectives over 3 years; identifies the responsible players (members, groups, Board, staff); the relevant KPIs and baseline targets, and, via feedback from key players in the network, assesses strategic progress for the Board’s overview and for Members’ information, every 6 months.

This (annual) Work Programme outlines all planned activities of each LINK group and subgroup, as well as plans for broader LINK meetings, workshops, receptions, initiatives and liaison.  Gathered in a single document so that everyone involved in LINK can see the intentions of the network and so as to identify where integration between work areas is needed, to strengthen impact, prevent duplication and contradiction.  It includes the programme of core work too.

The intention is that we report on progress, to the Board and to the Network, every 6 months in May and November.

Besides 5 strategic Group areas, and numerous Subgroups, there are 2 Forums operating more loosely as a valuable means of information sharing and capacity building for their members.

KEY to ACRONYMS

| MBs | Member Bodies (of LINK) |  | Strategic Groups |  |
| --- | --- | --- | --- | --- |
| Reps | The main Representatives appointed to LINK by the member organizations |  |  | Economics Group |
| GC/GVC | Conveners and Vice Conveners of the Groups |  |  | Governance Group |
| SGL/SGLD/FL/FD | Leaders and Deputes of the Subgroups and Forums |  |  | Land Group |
| CO | Chief Officer (Jen Anderson) |  |  | Marine Group |
| DO | Development Officer (Alice Walsh) |  |  | Planning Group |
| AM | Advocacy Manager (Daphne Vlastari) |  |  | Social Justice is a cross cutting theme, rather than a Group. |
| FOM | Finance & Office Manager (Karen Paterson) |  | Subgroups |  |
| AOA | Advocacy Office Administrator (Lisa Webb) |  |  | Aquaculture Subgroup |
| AO | Advocacy Officer (tbc) |  |  | Brexit Subgroup (part of Governance Group) |
| MPEOs | Marine Policy and Engagement Officer (Emilie Devenport) |  |  | Deer Subgroup |
| SEO | Sustainable Economics Officer (Phoebe Cochrane) |  |  | Food and Farming Subgroup |
|  |  |  |  | Hilltracks Subgroup |
| HF | LINK Honorary Fellow |  |  | Landscape Subgroup |
| StrG | Steering Group (Projects, Congress etc) |  |  | Land reform, land use Subgroup. |
|  |  |  |  | Legal Strategy Subgroup |
|  |  |  |  | Wildlife Subgroup incorporating Species Champions project, and National Ecological Network. |
| PSR | Political Strategy Report |  |  | Woodlands Subgroup |
| OS | Organisational Supporters |  |  | Wildlife Crime Subgroup |
|  |  |  | Forums |  |
|  |  |  |  | Media Forum |
|  |  |  |  | Scottish Environmental Fundraisers Forum |

| Current work area | Plans re: LINK objectives: improvement of national policy & implementation; improved capacity of network to contribute; effective network. | Specific tasks, targets, timings, advocacy strategy | Leader-ship and support | Staff roles/ Funding | Integration within LINK | Wider allies and liaison - Audiences | Progress |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Economics Group Vision: influence the current debate on economics in Scotland | The Circular Economy project is directed at creating new policy and legislation and ensuring implementation It will also significantly improve the capacity of the network to contribute in a policy area with which many member organisations are concerned but none have much capacity | Preparation of ground for a good circular economy bill, following confirmation of funding for a 3 day week Sustainable Economics Officer for 3 years, for the project A Circular Economy for a Fairer Future. The first year will be primarily for scoping within LINK to understand where member bodies work & LINK’s Groups & Subgroups, are relevant to the CE, while remaining live to current opportunities eg on plastics. Timetabling of the CE Bill is unclear so will also push on CE actions that can be taken without further legislation. Will invite an advisory group of external experts/interests to be a sounding board for the project. Initial event to share ideas with wider external interests once officer in post. National Performance Framework – Daphne Vlastari (AM) currently representing LINK on the Roundtable, aim to get better alignment with SDGs. Work on indicators ahead, will involve Wildlife SG and others. New NPF outcomes will be laid before Parliament in 2018. Preparatory work will be done for that debate. The Group will collaborate on areas led by participating member bodies - Natural Capital, the Scottish National Investment Bank, the Just Transition Commission, Deposit Return scheme. Issues remain of getting the value of nature recognised, and getting resources into green measures. | GC Matthew Crighton (FoES) GVC Bruce Wilson (SWT) RSPB, SWT, FoES, WWFS, APRS, MCS, HWDT, Hon Fellow J Curran. | 3 day week dedicated post. Advocacy, admin support required | Officer will consult with Groups/Subgroups about CE issues within their agendas. | Constituency of those who responded to the SNIB consultation. | The Circular Economy for a Fairer Footprint project has been taken through its scoping and preparatory phase. Meetings have been held with all relevant agencies. A number of background papers have been produced which have been considered by the Group. It was agreed to concentrate on CE issues in three sectors: • Agriculture and food • Plastics • Carbon (decommissioning and repowering) Regarding powers to deliver a CE, we have agreed to look into • options for using S82 of the Climate change Scotland Act to legislate for procurement of recyclate, and recycled and recyclable products • Look into scope for public procurement to do more and barriers The group contributed to the LINK position on the Environment Strategy and made a submission to the Deposit Return consultation. A briefing on the Scottish National Investment Bank was produced in advance of the debate in the Scottish Parliament on this topic. LINK has continued to advocate for improvements to and use of the National Performance Framework. The group continues to lend support to the activities of member organisations regarding economic issues. |
| Governance Group | Continuing to pursue all issues raised in Governance Matters as and when opportunities occur. Coordinating LINK effort on manifestos for UK, Scottish and Local Elections Coordinating LINK Brexit effort GG comprises: Brexit Subgroup – this correspondence group has been set up to ensure members are engaged and contributing to LINK work on Brexit as it goes forward. Legal strategy subgroup - There is a standing item on the GG agenda for an update from this subgroup. | Brexit –monitor development and impacts of Brexit beyond 2018 as necessary. Includes working with ELUK colleagues in joint Group monitoring Brexit and legislation, particularly. Also, monitoring and contributing to wider ENGO work through Greener UK Coalition (London based). Also speaking and advocating as Scottish Environment LINK on Scotland-specific issues. Want to ensure effective protections are maintained for natural and cultural heritage. Playing what part we can in relevant subgroup discussions of the Scottish Standing Council set up to focus on Brexit and implications for Scotland. Liaising with Scottish Brexit Minister, Mike Russell. Developing dialogue with Scottish MPs and MEPs. Inputting to academic thinking on needs of a ‘Scotland outside the EU’. Votes, legislation & processes impacting environmental governance Consensus building - Advocacy strategy around Brexit is under regular review. Lobbying regs implementation – Monitoring situation and inputting to working group which is developing guidance. Legal strategy The prospectus for an environmental law centre for Scotland will be published early spring 2018. Next steps likely: - workshop to develop key proposals in the prospectus, probably June 2018 - working to establish the ERCS as an independent SCIO and identifying trustees (including from LINK member groups) during 2018 - building on the prospectus to develop a strategy and business plan for the ERCS including a fundraising strategy for the ERSC and a set of policies including case selection criteria - finding funding to support this development work in 2018 Also pursuing idea of environmental courts in relation to Brexit through MSP liaison. Joined the Scottish Civil Justice Council taking forward thinking & recommendations on PEOs. With ELUK, Subgroup monitors UK’s compliance with Aarhus and submits evidence or follows up in ways as needed. Subgroup also inputting to an advisory group looking at how the Prog for Govt can lead by example in relation to social, cultural and environmental rights. This strand is likely to involve: running a wider event on environmental justice, Aarhus and the governance need in Scotland post-Brexit, possibly September 2018 | GC: Lloyd Austin RSPB Mary Church FoES leads Legal Subgroup. RSPBS, FOES, WWFS, Plantlife, SWT, occ. others contributing or supporting. Also Mark Lazarowicz HF and Ian Cowan lawyer (on legal strategy), & other legal practicioners. | CO, AM and AOA attend meetings, secretariat by AOA. Much of the GG work programme is directly linked to the AM who is heavily involved with the outputs. President roles overlap. HF M Lazarowicz assists on legal strategy. May request further DPF for legal strategy work. | Governance issues cut across all groups and subgroups so we involve others as relevant. On Brexit issues, we are liaising with all conveners. – the Legal Strategy subgroup is active and the GG convener also is on the Legal Strategy subgroup. | Legal experts (contacts have been made through the legal strategy subgroup inc legal academics, NGOs SCVO Electoral Commission, Others in civic sector – EEB – will be cc’d into referendum activity. Working with ELUK and the Greener UK Coalition Potential to work on environmental justice issues too with the other Links. | Brexit – Progress • All GG members continue to input and monitor Brexit developments. Daphne, Lloyd & Paul Walton are involved in ELUK and Greener UK discussions. Working to ensure that any UK outputs from G-UK are devolution-proofed. • LINK is continuing to liaise with Government officials on Brexit & related issues (eg Daphne & Charles Dundas meeting with Ian Jardine on 12 September & Daphne & Isobel Mercer meeting with the SG civil servants working on SIs on 22 June) • LINK responded to ScotGov’s ‘Developing an Environment Strategy’ consultation & LINK is represented on the Government’s External Reference Group for the strategy. LINK members also attended an environment strategy roundtable on 25 September. • On 18/4, Daphne gave evidence to the Finance & Constitution Committee on the UK trade bill. • LINK responded to the call for evidence by the Finance & Constitution Committee on common frameworks. • LINK contributed to the ELUK Response to Defra’s consultation ‘Environmental Principles and Governance after the UK leaves the European Union’, & members of the Brexit subgroup are seeking an IUCN mediated meeting of civil servants from all 4 countries to discuss frameworks and governance. • Planning & development of LINK’s Brexit campaign “Fight for Scotland’s Nature”, to call for a Scottish Environment Act, is underway. This will launch in autumn 2018 to coincide with the start of ScotGov’s consultation on environmental principles & governance. • Communications ongoing between Governance and other groups & subgroups where Brexit is relevant, and the FFSN campaign will necessitate input from all groups & subgroups to develop stories & case studies. Votes, legislation & processes impacting environmental governance Progress: LINK’s Campaign “Fight for Scotland’s Nature” will call for a Scottish Environment Act in order to address gaps in environmental governance following the UK’s withdrawal from the EU. Consensus building - Advocacy strategy around Brexit is under regular review. Lobbying regs implementation – Monitoring situation and inputting to working group which is developing guidance. Legal strategy Progress: The LS Subgroup contacted potential trustees, fundraisers etc who could be involved in the establishment of a law centre. A workshop took place on 1 October to explore capacity and support among those externals. The subgroup has approached Humza Yousaf MSP (Cabinet Secretary for Justice) for discussion of environmental courts. The plan for a wider event on environmental justice has been postponed for now, given capacity issues and also overlap with discussions which LINK anyway has with decision makers around Brexit. |
| Land Group Vision: Land management which meets SD goals. |  | 1. Land ownership and use – influencing land reform to integrate principles of sustainable land use & promoting the LUS. 2. Future of Scottish Agriculture – Progressing of LINK vision 3. Mainstreaming Biodiversity – through Species Champions advocacy and pursuance of the NEN. | GC Vicki Swales (RSPB), VC Diarmid Hearns NTS Active members – SWT, WTS, RSPB, NTS, Plantlife, SB, Nourish, APRS Ramblers, SCNP, SWLG, Trees for Life. | Core staff support ongoing. Advocacy support needed throughout the year. | Agenda crosses with Planning (land use); Marine and Governance (post-Brexit structures) Priority Subgroups: Land Use & Reform Food & Farming Wildlife. Others are Woodland, Deer, Wildlife Crime, Hilltracks. NEN work relates. |  | Meeting held September for overview and integration, with good representation from priority work areas and other Subgroups. See the relevant Subgroup reports below. |
| Marine Group Vision: healthy, well-managed seas, where wildlife is flourishing, ecosystems are protected, connected and thriving, and coastal communities are sustained. | Focussed on securing robust implementation of UK and Scottish legislation with all that entails including the opportunity for recovery of Scotland’s seas to ‘healthy’. | Encourage Scot Govt to progress Scotland’s Marine Protected Area network. This includes responding to the consultation on management measures for the remaining inshore MPAs & Special Areas of Conservation. At the same time LINK Marine Group will run a constructive public facing campaign to encourage public support & responses to the consultation. LINK will also encourage ScotGovt to progress with the designation of 4 outstanding ncMPAs, as well as 15 proposed SPAs. Engage with ScotGovt as they commence a work package to protect a subset of vulnerable Priority Marine Features outside of MPAs from fisheries. This was announced following damage to Loch Carron. Engage with ScotGovt as they review Scotland’s National Marine Plan. Engage with ScotGovt on the Fisheries Bill & other relevant legislation at UK level. Organise and deliver Sea Scotland Conference in June 2018, with partners. Engage as part of ELUK with sister Links, and through LINK members who are members of Greener UK, to ensure legislative & policy changes resulting from Brexit are fit for purpose. Aquaculture subgroup: joint LINK position document on Aquaculture in Scotland. Where possible jointly respond to SEPA consultations on Aquaculture regulation. | GC: Calum Duncan (MCS) GVC: Sarah Dolman (WDC) Members: HWDT; MCS; NTS; RSPB; RZSS (tho low capacity); SWT; WDC; WWFS S&TCS specifically interested in Aquaculture. Aquaculture leader: Sam Collin SWT Members MCS, SWT, NTS, WWF, S&TC, WDC | Funding for 1 FTE MPEOs to end 2019. Core staff involved in admin, HR, fundraising. AM inputs to advocacy strategy | Brexit related work is led by the Governance Group. Aquaculture – MBs active there also active in the MG allowing cross co-ordination. Wildlife Subgroup – indirectly through species champions initiative, potentially more so through NEN plans. need to develop LINK position on SG work to review protection for Priority Marine Features (no. 2 above). Initial call to start discs with 3 MBs & MPEO. MG plans to create a ‘prioritisation’ doc to guide further disc as a group at meetings/by email. Will meet Marine Scot by end Oct, which will inform our thinking & timescales. We expect that we will need to have reached ‘position’ by start 2018. Aquaculture sub-group – some time taken to achieve a consensus position, particularly in relation to tactics & positions on closed containment. | Orgs key for the Group to work with to build the case for environmental sustainability: Scottish Inshore Fisheries Trust; Scottish Creel Fishermen’s Federation; FFI Marine Community Support Project; Open Seas; COAST; Scottish Fishermen’s Federation and SWFPO. Community Alliance/Planning What scope is there to work with eg Links in the UK, EEB, IUCN and via other channels? What are your plans in relation? Ongoing regular communications with EL-UK Marine groups; members of the LINK Marine Group are also on the Greener UK Marine and Fisheries Vision group (MCS, RSPB and WWF) and the LINK Marine Group maintains close contact with the LINK Advocacy Manager who, with LWA of RSPB Scotland, is on the Greener UK Devolution group. Aquaculture: SEPA, Marine Scotland, Scottish Government. Scope to work with England and Wales Links to advocate adoption of the LINK Aquaculture Policy Paper after country specific additions and edits. | MPAs: LINK responded to the consultation to permanently designate the Loch Carron MPA and implement management measures for the site in June 2018, following the emergency designation in April 2017. Attending a workshop on the Strategic Environmental Assessment and Socio-Economic Impact Assessment for proposed management measures for outstanding inshore MPA sites, as well as submitting written comment. Planning e-advocacy campaign and co-ordinated LINK response to the 2nd tranche inshore management MPA/SAC fisheries management consultation. Developing and executing advocacy plans to support progression of four outstanding nature conservation Marine Protected Areas. Both of these topics are expected to be under consultation by the end of 2018. As part of the Species Champion 100 day Challenge, LINK members arranged a visit to St. Abbs National Nature Reserve for Species Champions to highlight the urgent need to progress with Scotland’s MPA network. This was attended by White-Beaked Dolphin Species Champion, Energy Minister and Regional MSP Paul Wheelhouse and other Regional MSPs Rachael Hamilton and Michelle Ballantyne, resulting in the recruitment of Michelle as a Species Champion for Atlantic Salmon. Further trips were arranged for marine Species Champions by RSPB, MCS and WDC. The Aquaculture subgroup have raised the collective concerns of Aquaculture within and around MPAs in their response to the ECCLR and REC Committee inquiries into Salmon Farming in Scotland (see Aquaculture subgroup report for further information). The LINK Marine Group have commissioned a report to review the effectiveness of proposed MPA Management Measures to inform effective MPA management in Scotland. Attended and contributed to LINK’s NEN and Protected Areas vision workshop on 2nd July. Staff and members attended a workshop to develop a Dolphin and Porpoise Conservation Strategy throughout the UK, on 19th – 20th April and contributed to an ELUK written response with UK colleagues. Marine Planning Attending a workshop and submitting written comment on the approach proposed by Scottish Government to review protection for Priority Marine Features outside of Scotland MPA network. The group carried out subsequent work to understand the distribution of relevant Priority Marine Features to inform discussion at a workshop held in August to develop alternative approaches to provide protection that were put forward in the Group’s response to the first public consultation on this topic. Supporting LINK Marine Staff who led on organising the successful 3rd Sea Scotland (2018) conference with external partners. The conference brought together a wide cross section of Scotland’s marine community to discuss the changing landscape for local governance and provide a platform for youth views on the marine environment. Attending as LINK the Clyde Marine Planning Partnership meetings 26 September, as well as reviewing and providing input in to the draft Clyde Marine Regional Plan and topic workshops (marine mammals, marine litter). Following on from the formal process to review the National Marine Plan, to which LINK members provided written evidence & met with relevant member of the Marine Scotland Marine Planning Department, MBs also attended a workshop help on Marine Planning in April. The group also liaised with the ECCLR Committee to discuss outstanding LINK concerns on the National Marine Plan and its implementation. This was followed by the submission of additional evidence on the inconsistencies within the Plan and a push for resourcing to develop Regional Marine Plans. Attending the Coastal Communities Network meeting to discuss Regional and National Marine Planning with Coastal Community Groups and understand their concerns, while also identifying and developing supportive networks for LINK marine advocacy. The Marine Group responded to the consultation on Seaweed Harvesting (Mechanical dredging for Kelp) in August. LINK responded to the consultation on the Offshore Wind Sectoral Marine Scoping Plan & have been invited to sit on the Steering Group to inform the development of this plan. LINK have also raised concerns on marine wildlife tourism with the Environment Cabinet Secretary and are preparing to meet with Minister Mairi Gougeon MSP in November. Fisheries: MBs continued to liaise with the S Gov Inshore and Sea Fisheries Teams at Marine Scotland to input to developing work on the future of fisheries management in Scotland. Attending and representing LINK at the Fisheries Innovation Scotland meeting on 9-10 July. MBs also contributed to the development of an ELUK and Greener UK response to the DEFRA consultation on the Fisheries White Paper. Following request for a meeting sent with MCS member magazine to Fergus Ewing, a constructive meeting was secured by MCS and attended by MCS, RSPB, WWF and WDC with the Rural Economy Cabinet Secretary. At this meeting, LINK members encouraged The Cabinet Secretary to set out next steps for managing fisheries in Scotland, which led to a commitment in the 2018-19 Programme for Government to start a national discussion to inform a consultation on the future of fisheries management in Scotland. Meeting with the MSC Team to arrange LINK involvement in the development of UK Fisheries Improvement Projects |
| Planning Group Vision: that the Scottish land use planning system contributes to a more environmentally sustainable society |  | Close engagement with Planning Bill to ensure it helps contribute to a sustainable Scotland. Group has very serious concerns with the legislative proposals as introduced, including no Right of Appeal for communities, scrutiny of the National Planning Framework, reduction of safeguards, & lack of integration with other policies eg climate & biodiversity. The Planning bill team supported by AM involving RSPB, PD, FoES, SWT & others where possible, is taking forward LINK action, including written submissions, a public e-action, coordination of amendments, and liaison meetings. Secondary legislation will follow. The Group will engage. | GC Aedán Smith, RSPB. GVC Clare Symons PD, APRS, BSCG, FOES, NTS, SWT, SWLG, SCNP, WTS. | Parliamentary support likely to be required during passage of the Planning Bill. | Gov’s stated intention is for planning to take on more of a leadership & coordinating role across govt so there will be some cross-over to all other groups. Most subgroups are relevant to an extent, particularly Hill Tracks, NEN, Landscape. | Depend on issue. Include sometimes RTPI, prominent individuals, Local Authorities Councillors, and communities. | Met regularly as Group, also with MSPs, SPAD and other interests holding weekly Bill Team calls for coordination during Stage 1 and 2 of the Planning Bill. The focus has been on influencing the progress of the Bill; through evidence; meeting MSPs, researchers, SpAds, on the direction of the Bill and our concerns; on the many amendments LINK and members have put forward; assisting with an event hosted by A Wightman MSP on Local Govt & Communities Committee; assisting PD’s wider media work & demonstration on ERA; organising a fringe event at the SNP conference on 8 October with funding from the DPF; holding weekly Bill Team calls for coordination during Stage 1 and 2. This has had positive results in that amendments have progressed through Stage 2 of the Bill process that would include a sustainable development purpose for the Bill tied to national outcomes, improved Parliamentary scrutiny for the National Planning Framework, retention of Strategic Development Plans (which were to be scrapped and partially incorporated into the NPF), and a clampdown on repeat applications from developers. The Govt remains opposed to Equal Rights of Appeal, though support is growing among SNP councillors, and within opposition parties. Stage 2 will be finished in November, and Stage 3 completed by the year end. The Planning Group will meet on 15 November to discuss its forward plans. |
| Climate |  | Supporting Stop Climate Chaos Scotland asks on the Climate Bill, complementing with specific advocacy around biodiversity, land use, NEN, marine and more. | Advocacy Team & WS leader, with input from Groups & Subgroups. | AO focus. | Is cross cutting. |  | LINK responded to the call for evidence by the Environment, Climate Change and Land Reform Committee on the Climate Change (Emissions Reduction Targets) (Scotland) Bill in August. We took the opportunity to highlight LINK’s asks in relation to biodiversity and land use. LINK commissioned a report to collate and present evidence on the impacts of climate change on species and habitats in Scotland. The aim is for the report to be finalised in January, before Stage 2 of the Bill to support our advocacy asks. |
| Aquaculture Subgroup |  |  | Leader: Sam Collin (SWT) Depute: Dawn Purchase (MCS) Member bodies: NTS, WDC, HWDT, WWF |  | The aquaculture subgroup is active through the Marine Group |  | Submitted advice to the REC Committee’s inquiry into salmon farming in April 2018. Awaiting publication of REC report and SEPA’s Sectoral Plan, both expected by end October. Subgroup workplan will be developed once these have been published. In the last six months, Marine Scotland have produced a Farmed Fish Health Framework, which contains four working groups. Although LINK have not been invited to join these working groups, we will be closely monitoring their discussions and outputs – membership of these groups will be reviewed in the early stages, with LINK possibly being offered a place later. The subgroup has a place on Marine Scotland’s ‘Wild Fish Interactions Working Group’, which Sam Collin will attend (or by another subgroup member if not available). We will look to engage more with industry once Working Groups are up and running. We have started regular meetings with Marine Scotland’s aquaculture team – so far two meetings have been organised, with meetings expected every 6-8 weeks. We have met with SEPA to discuss their new approach for modelling waste from salmon farms. A meeting with SEPA will be arranged once their Sector Plan consultation has opened. LINK Marine Group met with coastal communities (including Friends of the Sound of Jura and Save Seil Sound) to discuss the use of acoustic deterrent devices on salmon farms. We have begun regular discussions with Alan Wells at Fisheries Management Scotland on the future of salmon farming and updating each other on our positions/activities. |
| Deer Subgroup Vision: Ensure sustainable populations of native deer species which play positive roles in Scottish ecosystems & contribute to rural economy |  | Contribute to work of Land Group insofar as deer management is relevant. Engaging with new independent deer panel announced in the Programme for Govt Sept 2017. Evidence and attendance at stakeholder workshops. Subgroup has agreed position statement on sustainable deer management. Our main target in coming months will be above review group. Contribute to SNH Wild Deer Strategy targets and reporting. Attend SNH Deer Management Round Table. | Duncan Orr-Ewing, Chair. Maggie Keegan, Depute. MBs: RSPB, SWT, NTS, RS, TfL, PL, WTS, RZSS Also Mike Daniels JMT. |  | Work sits within the focus of the Land Group. We develop consensus around all outputs, usually either face to face or by email. We have a good track record of producing agreed evidence for Parliamentary & other committees, delivering real impact. | SNH Scottish Government ADMG Forestry Policy Group Routine engagement with SNH (Wildlife Management), Scottish Government (Habitats and Species). | Main actions: Contributing to initial phase of SNH review of deer code via response to online questionnaire. Independent deer management enquiry. In some limbo following death of Simon Pepper who has chairing this enquiry. Also preparing for SNH report to SG on DMG performance due in 2019. Contribution in due course to deer management components of LINK response to Forestry Strategy. |
| Food & Farming Subgroup Vision: Working for sustainable agricultural systems that produce supplies of safe healthy food, protect natural resources & enhance wildlife, habitats & cultural heritage, & provide jobs in rural areas, contributing to a diverse rural economy |  | - Develop document setting out high-level principles for future policy in collaboration with SLE (in process) - Public polling and potentially some focus groups with strong advocacy plan for communicating the results. The polling work will feed into developing an advocacy plan around Post-Brexit policy as new thinking and strategies emerge. - Potential farm scenario workshop – using whole farm plans/ILMPs to draw out “average” farms in different areas and sectors and creatively assess how these farms would plan their businesses in light of new policy designs. Decision taken to delay this - would probably not take place until later in the year at the earliest, as would be most useful when we have a clearer picture of the direction of travel. -Potential events, options include – o Parliamentary reception with keynote speaker (Karl Falkenberg, someone from OECD, FAO, etc) followed by LINK speaker on our policy design o Parliamentary reception in collaboration with SLE (could take similar format to above) o Parliamentary seminar to include an explanation and Q&A of our future policy design Advocacy Strategy: Doc on high level principles: being developed in conjunction with SLE. Advocacy point to work collaboratively with other rural stakeholders. Continuing work with SLE will be beneficial as they bridge the gap between land use for public interest & landowning communities. Public polling: Will need to be communicated effectively & sensitively to the results of the polling, but consequently advocacy will depend on the results of the polling. Depending on the outcome, it can be used both in behind the scenes advocacy as well as publicly, in press releases, blog posts & to support new work on future rural policy. Post-Brexit policy: Aim to build momentum on post-Brexit policy & reform of rural policy. Possibility of engaging individual members of our respective orgs in writing to their MSP & asking them to attend event. Needs: - may consult with more campaign-oriented members of the group such as WWF or FoES | Leader Pete Ritchie ( Depute Anna Brand. Active Nourish, RSPB, SWT, NTS, Plantlife ScotFWAG, APRS, Soil Ass. Corresponding members: ARC, BES BBCT, BC, SAGS, WTS. | Contribution secured for public polling. | Pete Ritchie, Vicki Swales are on the Land Group. | Potential for engagement with SNH for the farm scenario workshop, particularly in relation to their new project ‘Engaging farmers in biodiversity solutions’. This is run by Graduate Placement Kirsten Brewster, managed by Jenny Johnson in agriculture team. | Polling – a poll was carried out with 1000 people by Survation. The results were published in April 2018 and picked up in a positive 2-page spread in the Scotsman on 3 May. This has been used for advocacy since, and been mentioned in reports from government groups, e.g. the Agriculture Champions. Post-Brexit policy – Stakeholder workshop run at Battleby in June 2018. Had ca. 30 colleagues in the room, including from director level. Positive discussion on how things could be done differently, but many different voices and needs in the room. Within LINK, a workshop process over the summer resulted in the production of a narrative on what we mean by public goods, written by Scott Leatham of SWT. This is being carried on trying to put more detail to our policy position, with member organisations taking on chunks of work. A LINK response to Scottish Government’s Stability and Simplicity consultation was also submitted. Members attended LINK Land Group Workshop on 13 September. Political engagement – Several MSP meetings have been held over the summer and are in diaries for the Autumn. A delegation met with Fergus Ewing in June to discuss policy. Principles document – a document on the principals of post-Brexit funding was in development. However, this has stalled somewhat due to staff changes in SLE and other time constraints. Therefore, this is no longer being as actively prioritised. Further advocacy plans are being developed in response to announcements in Parliament. On 26 September, Fergus Ewing announced plans for a simplification task force and a debate in Parliament on the principles of future farm support. Engagement with Fergus Ewing and MSPs is being planned both as a response to this and in continuing to advocate for the suggestions we made in the ‘Stability and Simplicity’ consultation. |
| Hilltracks Subgroup | We will be producing a report which evaluates the success of the prior notification system, based on 3 years of monitoring planning authority websites and engaging with stakeholders. Our activities over the following period will be focussed around discussing this report with other stakeholders and building support for our recommendations. | Actions: 1. Our formal monitoring of planning authorities’ websites for prior notifications, prior approvals & planning applications relating to Hilltracks will likely end in April/May 2018, but we are considering how / whether to continue with this monitoring in future. 2. We will continue to highlight and investigate any cases of bad practice that we are alerted to via members of the public. 3. In May we will be publishing a report of our 3-years of monitoring of this legislation with recommendations for ways to improve the current planning process. 4. We have an advocacy strategy for this period but will be drawing up a more detailed communications plan for disseminating this report and ensuring we gather widespread support. Which Scottish organisations are key to build your case for environmental sustainability? What are the plans and timescales to develop or extend these relationships? Scottish Govt, SNH, FCS, national parks & key local authorities are all relevant, plus forestry bodies like CONFOR & landowning interests SLE, NFUS. We met SLE in October 2017 and have arranged meetings in April/May with SNH, Scottish Land Commission and LLTNPA. We also plan to meet Confor and political allies following the publication of our report. | Helen Todd & Beryl Leatherland co-leaders. Members: RS, SWLG, NEMT, CC, APRS, SCNP, NTS,RSPB and BSCG. Huge support continues to be given by George Allan of NEMT Hilltracks consultant, Mel Nicoll until May 2018 and a group of volunteer ‘Trackers’. | Staff support from FOM for managing funds & paying consultant, & updates to webpages. Will seek support and advice from AM on advocacy plans as they are updated. No training or long-term support needs. | Relevant to Planning Group and Land Group (via Land use/reform/landscape sub groups) | We are supported by non- LINK bodies like John Muir Trust, Mountaineering Scotland & the Munro Society, in terms of liaising over hydro scheme tracks & helping to promote our campaign. We will meet Simon Brook, SNH during this period, as part of the Landscape subgroup, to update him on our campaign. We have been in close touch particularly with CNPA over various Hilltracks within the park & are likely to continue to do so, while we will meet LLTNPA in May. | Advocacy Plan was followed including interviews with Confor, NFU, SNH [by phone, meeting & a follow up], Scottish Government planner, LLTNPA planning team, CNPA planning team and MSPs Andy Wightman, Graham Simpson and Alex Cole-Hamilton. We did not manage to arrange any meetings with other members of the LGCC. Subsequent to the letter to Roseanna Cunningham, Cabinet Secretary, in relation to the relevance of the campaign to the Grouse Moor Review Panel, there has been a brief informal discussion with her. A copy of the report has been sent to the panel. Campaign members communicated by email only during this phase of work although one meeting was held between the core workers [Ramblers, NEMT, SWLG] and the consultant. As we changed our original plan to release the report in the spring in order to link the aspiration of the campaign to take advantage of the Planning Bill progressing through parliament, this enabled a longer period of monitoring and assimilation of evidence and case histories, so additional funding was raised to enable the consultant to be engaged for longer. During this period the volunteer monitors [“trackers”] have been kept informed and engaged, and their input has been invaluable. The two external funders have been sent six-monthly reports on progress and plans. As a result of our meeting with him, Andy Wightman MSP and a member of the LGCC, has put in an amendment to the Planning Bill [No 165] which is quite targeted and while not exactly in line with our asks, would be a welcome change if it gets through at Stage 2. Report was completed by the external Consultant and launched 18 September, together with a press release. This generated a huge amount of traffic on social media and the relevant blog sites as well as in the printed press including the times and smaller local papers. Helen Todd was interviewed for BBC Scotland [TV and radio] and both co-convenors have been interviewed together by Mark Stephen of BBC Out of Doors. The report was circulated electronically to a wide range of stakeholders and hard copies have been sent to the Cabinet Secretaries, the Planning Minister, all members of the LGCC, SG planner, SNH, the CNPA, and some stakeholders. All LINK member organisations & Hon fellows have been sent a pdf copy. Interested externals, members of the public who have sent relevant material and the planning departments of the 11 local authorities monitored have also been sent a pdf. We will shortly to finalise 2 related Annex documents, (a) on how the Prior Notification process could be improved and (b) on wider concerns related to track construction in Scotland. These will circulate to a more limited number of stakeholders, primarily planning authorities, SNH, Scottish Government and national parks. No additional communications or engagement work is anticipated. |
| Landscape Subgroup |  | 1. Not yet decided how to best promote the Landscape & Wind Energy Statement of 2016 & which bodies and audiences should be targeted. 2. Discussed holding or series of topic based events culminating in a conference 2019, in assocn with other [non-LINK] orgs, to raise the profile & awareness of & a commitment to landscape issues. Timing appropriate due to several SG related initiatives & activities [LUS, possible Vision for the Uplands, recent consultations on WLA matters, moorland management]. Aim to create momentum on particular themes as part of the prep such as the health agenda, importance of landscape to tourism, culture, recreation & thereby to cumulatively build up the case for landscape. Strategy doc (Tending the Goose) outlines. D Hearns coordinating in 1st instance. 3. Promotion of the Scottish Landscape Charter - this will need some review and update. 4. Will continue to support the work done by APRS & SCNP in their campaign to achieve the establishment of additional NPs in Scotland. 5. Our member bodies have continued to support the Hilltracks work particularly in awareness raising & promotion. | Leader: John Thomson Depute: Beryl Leatherland, Members: RS, SWLG, NEMT, APRS, SCNP, NTS. Bob Aitken, Honorary Fellow interested. | We may need support from more HFs. If holding a conference maybe cost implications but external funding will be sought. Such a Conference & precursor events & activities may contribute to an alternative set of outputs from SEW, as has been proposed. Will seek AM advice on revision of our advocacy plan. | Relevant to: Planning Group & Land Group (via Land use/reform/possible SG Upland Vision/issues around grouse moorland management having a higher profile with Cab Sec involvement | Allies: SNH, JMT, LIS, Hutton Institute? Other LINK member bodies? | Not yet decided how best to review and promote the Landscape and Wind Energy Statement of 2016. Wider issue of promoting Landscape interests: specific actions are being drawn up by NTS [Stuart Brooks] and LIS [Rachel Tennant] and we are awaiting these to be disseminated for discussion and taking forward. Advocacy around promoting landscape interests to a wider audience will involve working with a range of interested parties, government, politicians, statutory bodies and wider civic society. This will probably necessitate several groups of different interest areas being set up under the umbrella of a Landscape Alliance. No firm plans or structure yet, we are awaiting proposals from NTS and LIS. Obvious implications here for LINK working and protocol, so proceeding with great caution. |
| Land Reform & Land Use Subgroup Vision: taking a bigger look at these issues in the round | Objectives: Get SG to deliver Policy 7 and Proposal 1 of the LUS - support establishment of regional partnerships and roll out of regional land use frameworks Objective: To ensure that environmental interests and goals receive adequate attention in the implementation and further development of the land reform agenda. Objective: To ensure that landscape interests and goals are adequately recognised in the development of land use thinking and policy, both within LINK and more widely, and are integral to any approaches proposed. | Land Use Strategy: Given the absence of any activity on Scottish Government’s part, the Subgroup sees a need to stir things up over the coming 6 months. Actions envisaged include: - finalising in April a short paper summarising the benefits of integrated land use and management and its relevance to a range of SG priorities - drawing the lack of progress to the attention of the Director of EnFor - raising the issue at the LINK meeting with the CabSec (Roseanna Cunningham) scheduled for 27th April - exploring with the Forum for Natural Capital the possibility of funding a conference on land use planning and management in autumn 2018 - exploring with SLE its interest in continuing to collaborate in this area of work - combining all the above with a publicity campaign to promote the benefits of integrated land use planning and to embarrass SG into action on the LUS In addition the Subgroup also sees merit in the development of an Upland Vision – an option previously floated by SG but seemingly now in limbo. This is a matter which should also be raised with the CabSec. Land Reform: The Subgroup will continue to monitor the activities of the Land Commission and to maintain contact with key staff (a meeting with its CEO, Hamish Trench, is scheduled for 24th April). One area currently being investigated by the Commission identified as being of potential interest to the Subgroup is land value taxation. The possibility of some LINK activity in this field is being raised with the Economics Group. Landscape: As of now the Subgroup is essentially maintaining a watching brief on work being undertaken by the Landscape Subgroup and a wider alliance of bodies with an interest in landscape matters. But it remains desirable to identify and seize opportunities to incorporate landscape objectives within the more holistic approach to land use and management advocated by the Subgroup. | Leader: John Thomson Depute: Sheila George Composition of Subgroup will vary with the topic(s) under discussion (Key contributors on land reform are RSPB, NTS, WTS, APRS, SCNP, Ramblers, SAGS; on LUS same plus Buglife, Plantlife & SWT; & on landscape APRS, CC, NEMT, NTS, SCNP, SWLG. On all topics, however, broadest engagement welcomed. | Resources: MB time, LINK AM to help & advise on devising & implementing advocacy plans, securing meetings with politicians, visits. Promotion of summary paper (longer paper already on LINK website). | The Subgroup will report to the Land Group but Planning Group and Governance Group may also be consulted as required. Any work in the field of land value taxation would involve collaboration with the Economics Group. | Targets: Cab Secs for ECCLR and RAC; MSPs, Keith Connal, Land Commission, SEPA, SNH, NFUS Allies: SL&E, some local authorities (Highland, Western Isles, East Lothian, North Ayrshire, Borders, Aberdeenshire), Tweed Forum, National Parks, potentially Confor | Efforts to press SG into renewed activity on the Land Use Strategy front finally paid off when Katriona Carmichael was given a brief at Deputy Director level to take the initiative forward. Since taking up the role in the summer she has engaged actively with LINK members and with other non-LINK bodies with relevant experience and expertise and environmental credentials (eg Tweed Forum, Southern Uplands Partnership, Galloway and Southern Ayrshire Biosphere). The upshot was a stakeholder engagement meeting in September, convened and chaired by the Subgroup but attended by a wide range of public and third sector bodies. This focused very positively on how the LUS and land reform agendas might together drive a future approach to land use policy based much more firmly on the principles of integrated, multi-benefit management and payment for the delivery of public goods identified through an inclusive, participative process. The intention now is to follow up the positive engagement established, especially with relevant ScotGov staff and with the Land Commission. Land reform: met Hamish Trench, CEO of Land Commission, 24 April, discussed extent of shared interest in implementation of LUS and in promoting environmentally responsible land management. Fed into subsequent dialogue. |
| Wildlife Subgroup Vision: Scotland’s natural heritage (land & sea) is complete in its diversity, with fully functioning ecosystems & resilient to accelerated environmental change. Wildlife Crime Subgroup Woodland Subgroup | Action: Planning to further develop the Species Champions initiative with support from an intern Calum Langdale. All groups can be involved in this. National Ecological Network development will continue. Biodiversity Funding – we will produce evidence and communicate the need for continued, secure funding for biodiversity action in Scotland. Will potentially need to do some work on protected areas. Advocacy Strategy: objective to ensure that nature conservation is no longer marginalised & that the SGov & SNH recognise the importance of biodiversity & invests in it appropriately. Need to influence the 2018/19 SGovt budget. Will mobilise Species Champions to support the inclusion of sufficient funding in the 2018/19 budget. Needs for briefings are an Independent assessment of progress on Route Map? Economic analysis? Measures of success: SNH budget for nature conservation is increased; biological outcomes are at the heart of grant priorities. |  | Leader: Craig Macadam, Depute: Caroline Griffin, MBs: Buglife, Bb Cons Trust, Bat Cons Trust, Butterfly Cons, Froglife, MCS, WTS, RSPB, SWT, Plantlife, BES, BSCG, NTS, RZSS, SBT. | Honorary Fellows regularly attend meetings. The Species Champion intern will be managed by the Advocacy Officer. Have had previous support from the RSPB advocacy team, now more ltd capacity so this may be challenging. | NEN - Land, Planning and Marine Groups | Audiences: Cab Sec Envt; ECCLR committee; SGovt Envt & Forestry Directorate; SNH; SEPA; FCS; Marine Scot; media Allies: LINK members, Species Champions, LBAP officers(?) | Species Champions Initiative: 100 day challenge ran from 5 June to 12 September and had many successes: • All host organisations took part in the challenge in some form • Many events were co-operated between LINK MBs. • In total there were, 38 site visits and engagement events with two involving ‘cross party’ engagement • In total, 58% of MSP’s engaged in the 100 day challenge • 72 MSP’s have now engaged with their species over the last 18 months (this included 14 MSPs who engaged with their species for the first time) • Twitter posts from the species champion twitter account reached almost 200,000 people during the 100 day period • The campaign culminated in a lunchtime Parliamentary event with 33 MSP’s and 70 other guests attending to celebrate the success of the challenge • Further interest in initiative from four MSP’s currently without a species Pleased that funding through DPF has extended the employment of Species Champion Co-ordinator, Calum Langdale, for a further 12 months. Biodiversity Funding: Craig and Daphne met with clerks of the ECCLR committee to discuss the background to concerns around biodiversity delivery in Scotland. The ECCLR Committee has advised that they will continue to ask questions of SNH about funding for biodiversity, particularly in light of the Aichi report findings. National Ecological Network: Despite agreement across LINK and SNH the development of the NEN has stalled somewhat due to what we believe are misunderstandings about what the NEN will look like. We held a workshop for LINK members to discuss way forward and we are looking to pull together a paper on what the NEN means for various sectors. This will then form the basis of our advocacy going forward. Biodiversity post 2020 Initial discussions amongst members about what the next Scottish Biodiversity Strategy should look like. General agreement that the NEN should form the basis for the post 2020 route map. The subgroup plan to create a conceptual map to help visualise the NEN and incorporate the NEN into different policy areas and bills/acts going through Parliament. |
|  | 1) Canvass more interest and support from wider membership, as the SubGroup can feel quite isolated, & in quite a narrow field. Environmental & wildlife crime occurs within all habitats and species 2) Scottish Government’s 2016 Wildlife Crime report responded to by Jan 2018; close contact maintained with ECCLR Committee. The response to be widely shared with MSPs and Species Champions. Closer contact and co-ordination being sought with both Police Scotland and Crown office over future crime figures being shared before publication. 3) Plan wider interventions, e.g. through Scottish Parliament’s Justice Committee 4) Exert political pressure for the SNP manifesto commitment for a Scottish Wildlife Crime Unit to be enacted. 5) Links with Wildlife Group to be strengthened, and more communication with other LINK possible members. Advocacy strategy: A coherent Advocacy Strategy is currently being developed, with the help of the AM |  | Leader: Eddie Palmer. Depute: Ian Thomson Members: RSPB, SB, BCT, SWLG, SWT, NTS, SCRA, Froglife, SRSG, WDC, Buglife. |  | Unsure yet |  | Little progress on aim to persuade Scottish Government to adopt the SNP’s manifesto Commitment to form a Scottish Wildlife Crime Task Force within Police Scotland. The Species Champion for Badgers, Colin Smyth, MSP, has been very helpful in asking PQs, aided by LINK’s Advocacy staff. The apparent commitment was dropped during this period, communicated by a civil servant during a meeting with LINK representatives. Plans are now to review the two LINK reports, 2014, ‘Natural Injustice’. |
|  | We will continue to work with FCS on the delivery of the completed Mackinnon Review actions into 2018. We will engage with the creation of the new Scottish Forestry Strategy in 2018. We will engage with both FCS and FES to ensure that the work they do is in the best interests of the environment. We will also monitor the success of the new Governance arrangements of FCS and FES as the SG’s Forestry Division and the Forest and Land Scotland agency respectively, staring in 2019 (this will be relevant to both the Land and Governance Groups.) We will engage with the development of a Corporate Plan for Forestry and Land Scotland in 2019. |  | Leader: Charles Dundas WTS Depute: Sian Williams RSPB Members: WTS, TfL, RSPB, Plantlife, BCS, NTS, SWT | None |  | Forestry Commission Scotland, Scottish Government, SLE, NFUS. Our concerns are domestic to Scotland. | Nothing to report. |
| Media Forum | For staff/volunteers in the network who deal with media, to exchange information, build capacity & influence agenda. |  | up to 18 MBs on 2016 list – | Understanding shared by LINK CO with media forum is that it needs to be self-serving, rotating its convener potentially | Has potential to involve and be of use to any member and to LINK’s groups and subgroups | Is intended to be an internal intel- and experience-sharing forum, to build capacity to influence the media agenda regarding the environment. | Has not met in the last 18 months though one attempt made to hold a meeting focussed on social media. There is appetite among some members for meetings. And a suggestion to broaden title to ‘Communications Forum’ as a better reflection of people’s work – web, social media, ecomms, digital ads, etc. Has been encouraged to self-sustain and this seems appropriate. At autumn 2018, LINK staff capacity is fully absorbed elsewhere. |
| Scottish Environment Fundraisers Forum | Facilitate partnership between fundraisers in LINK to share info, experience & under-standing of sources of funding for Scotland’s environment. | Meetings are quarterly, normally with a guest speaker. All MBs with staff with fundraising responsibilities are welcome to participate. | FL: Steven Gardner (SWT). FLD: Alison Connolly (RSPB). Minutes: Dianne Laing Many MBs on the email list | No need for support anticipated from LINK staff. DPF funding sought for video to make Scotland’s case for funding with UK trusts. |  |  | SEFF met twice - on 7 June & 6 September. At the June meeting the group has a meeting/presentation with Lindsay Wells from SEPA on the topic of the Scottish Landfill Communities Fund and in September the group had a meeting/presentation with Will Humpington from Peoples Postcode Lottery on their Climate Change & Environmental Programmes. The group commissioned a film – This Is Scotland to take forward the findings from the WTGGW Scotland report and make the case for increased funding to support Scotland’s environment sector. Some SEFF member bodies contributed financially, LINK provided funding support and an external body provided a grant. |

| Other work / initiatives / events involving Member Bodies and Groups/Subgroups, Trustees, Staff |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work area | Action towards objectives: improvement of national policy and implementation; improved capacity of network to contribute; & effective network. | Specific tasks, targets, timings and indicators of progress where provided | KPIs relevant | Leader-ship and support | Staff roles/ Funding | Integration within LINK | Wider allies and liaison | Progress |
| Network meetings 2018 AGM 2018 | 2 pa. May & December, December 2018 Elect trustees, appoint President & HFs, present annual report & accounts, ratify subscriptions | To bring players together with board and staff to review progress, discuss learning, reassess political and other contexts, do SWOT analysis, ensure update between members, reports to board and network from the Groups and Subgroups, discussion of integration needs, resource issues, review of priorities and adjust forward plans and advocacy strategy Members’ annual meeting to hear a report from the board, discuss the annual report, agree subscriptions for future year(s), elect trustees and appoint any fellows and/or president |  | CO CO & FOM, with Treasurer Board discussions | Led by CO Support from FOM DO produces summary version of report | Network meetings cross the range of work 2nd of these is attached to annual general meeting and festive reception | Occ. invited audience to Networks. AGM open to members | Meeting held on 10 May, well attended. Useful discussion, with reps of key groups and subgroups, assessing LINK impact around Brexit, hearing update on Brexit campaign plans; also checking and adjusting integration intents, advocacy plans here and there. AGM will be on 7 December. Report and accounts were published in August in both full and summary form. The Board has carried out a review of subscriptions, consulting with members on issues and more recently on a proposed recommendation. Preparation in terms of trustee rotation, possible Fellow appointments is in hand. President Joyce McMillan has confirmed that she can offer LINK a further year (to autumn 2019). |
| Congress 2018 | Annual event for building community among member bodies and informing network on issues of overarching interest. | Theme usually identified early spring Steering group of volunteers from among board, staff and groups usually assists |  | DO with steering group of trustees | Delivered by staff. | Theme stems from key priorities. | Externals invited as relevant to theme. | Helen S, Beryl L & Clare S were the St Group. The theme was Inspiring Success, sharing lessons of successful environmental campaigns following the members advocacy training day on 30 August also focussing on campaigning. The training was at capacity (40). Dinner and speed talks format worked well. Over 60 people came including several guests from SNH, SEPA & others. |
| Fundraising | Future of existing projects and support for other work relies on fundraising. | Fundraising ongoing. |  | Several staff & group leads |  |  |  | Work continues with the Marine St Group to ensure there will be funding from the end of 2019 for the Marine project, with plans for funders and fundees meeting on 12 December. Meeting TBA with contacts in SNH and SGov for next year’s grant. |
| LINK Local (2016 to 2018) | A pilot project which ran for 2 years from 2016 | Set up spring 2016 after 18 months’ discussion and planning in LINK. Aimed to assess value/need and potential use of LINK Local database (website). Thinking was to connect local environment action to national level NGO work, and to encourage local environment groups to be able to find both local equivalents and national contacts via a database. |  | CO, FOM leading. AM, DO inputting |  | Being monitored | HEN, SCA, FFI among other | Further to internal review and an alert to the Board, LINK Local participants were informed of LINK’s decision to end this pilot in August, with information on other avenues for those interested. The Facebook page is now closed. Some local groups have opted to stay on an email list for general information. |
| Workshops on topics prioritised by members and/or Board | Scope views on where collective work can address gaps identified by strategic planning. Keep watching brief for topics needing ‘work-shopped’ and add these to plan as agreed. | Open to any Group/Subgroup to propose and hold. Staff may also coordinate. Sometimes involving other allies/partners. Often workshopping views within LINK towards collective positioning. |  | Staff organise & pursue as resources allow | Delivered by staff in conj with Group leads. | Open to all members | Topic specific, and for organisers to determine | Workshop held on Land Use Strategy (see above) on 13 September. Environment Campaign briefing for CEOs held in July. Legal Strategy wider meeting held 1 October. Forestry Strategy meeting tb held in November. |
| LINK Receptions 2018 | With audiences across the sectors to celebrate work in which we are all involved, providing networking and soft lobbying opportunities. | Excellent Scottish Environment Reception held in Parliament on 17 April – which timing we will seek to continue annually. Festive Reception planned for December 2018 in conjunction with AGM and Strategic Planning meeting, deliberately, with aim of attracting membership. |  | AOA & DO | Sponsorship & organisation | Open to all members | Relationship -building | Species Champions event in the Parliament on 13 September was well attended. |
| Strategic liaison | Board / President level development of relationships with wider policy community. | Revised Strategy indicates more relationship building would be beneficial, including at Board level. Liaison also continues regularly with various sectors at Group and Subgroup level. |  | Board, Groups, Staff |  |  | Relationship- building for stronger advocacy | SNH liaison held summer, with further dialogue planned on key issues of concern to LINK. Meetings with Head of SG Environment Dcte held. Board intend to develop liaison with Crown Estate and VisitScotland. SEPA meeting in early 2019 in diaries. |
| LINK Parliamentary events | Programme of events over the year linked to priorities, supported by Advocacy Team. Addressing cross-party parliamentary audiences on issues prioritised by LINK Groups | Up to 4 per year is our plan, in the wake of a change to the annual SEW which is no longer a week’s events, and simply one reception. Topics to be identified. Timing – across the year. |  | AOA & AM with input from others |  |  |  | Species Champions event was well attended and helped the profile of the scheme – 13 September. |
| Environment Links UK | Federal working with the other 3 Links on UK issues. Informed by MOU and ELUK strategy, this involves regular liaison designed to help each Link improve services & to support all the Links in their relationship building & advocacy at country-level, & with UK and EU audiences | Federal collaboration on: - Brexit ELUK group & Greener UK coalition - Marine (via Links’ marine groups) - Other policy areas Connecting with Irish Environmental Network Sharing info on operations, funding, protocols, etc |  | CO, AM, GCs, SGLs & Trustees | Delivered by staff, some Groups players, trustees | Network kept informed of joint initiatives, and progress at strategic level | WCL, NIEL, WEL are the main allies. Irish Environmental N/W perhaps? | Good liaison with ELUK and GUK over Brexit (see Governance report). Very good ELUK conference held 3 October in London on SDGs. Contact between Links on circular economy and on climate will develop as a result. There is close contact between the Links on marine issues. ELUK also combined for a meeting with Heritage Lottery and submission to its consultation. Sharing of intel and experience goes on regularly among the 4 directors. |
| EEB, IUCN and other international bodies | Use / develop LINK use of these bodies in relation to post-Brexit needs | Governance Group is intended to hold overview on such relationships. LINK is organising a separate discussion of international needs and Scotland-focussed thinktanks, at autumn 2018. LINK is active within the EEB via Advocacy Manager and Lloyd Austin as EEB’s UK board member (at least until 2019). |  | CO, AM, LINK delegates |  |  | Relationship- building for stronger advocacy | Governance Group seeking IUCN help in getting 4 countries together on UK Frameworks. Daphne & Lloyd attending EEB conference Nov. LINK event planned for October to consider environmental needs in terms of international coalitions, and nationally-focussed thinktanks. |