## Master 2020 work plan
Activity / tasks | Timetable | Performance target (KPI) | Group leadership | Progress assessment | Outcome | Other relevant LINK Groups | Partners to work with
Strategic objective 1: Sustainable Scotland
Use SG Deer report & LINK Deer report to embed apppropriate deer management policy into govt agency action and legislation | March - April |  | Deer |  | Govt agencies remove fencing and increase culling; culling targets to halt env degradation & increase regeneration are legally binding | Land use | FLS, FS, ECLR
Engage with coalition members and MSPs on amendments to CE Bill | March - April |  | Economic |  | A CE Bill with targets and in line with LINK asks. Bill withdrawn due to Covid. |  | Circular Scotland coalition; MSPs
Work with SG to transpose / integrate better waste regulations through amended EU Waste Directive, single use plastic Directive & food waste | March - June |  | Economic |  | increase in re-use measures and full implementation of Directives | Marine
Agriculture (Retained EU Law and Data) (Scotland) Bill. | Jan-Nov 2020 |  | Food and Farming | Stage 3 to come. Objectives so far not achieved | Amendments to insert a purpose clause into Bill and commitment to non-regression included in final legislation. |  | NFUS, SLE
Good Food Nation Bill & broader agenda: to halt environmental impact of food production and consumption including fish & shellfish | expected April |  | Food and Farming |  | LINK policies recommended by committee and amendents adopted. GFN Bill withdrawn due to Covid | Aquaculture Group | Scottish Food Coalition
Contribute to Agricultural Transformation Programme for farming and food production thorugh LINK position on how the Transformation Programme should be spent | April onwards |  | Food and Farming |  | MSPs aware of LINK asks and push for incorporation during Climate Plan scrutiny. | Land Use group
Respond to second tranche of conversion funding | Autumn 2020 |  | Food and Farming |  | Ministers use funding to promote good environmental outcomes, eg support Rural Land Use Partnerships | Land use group | SLC
Work with SG for strong Continuity Bill. Work up amendments on strength of duty on principles, independence, power & function of watchdog, legal underpinning of strategy & retention of targets | March - Nov |  | Governance |  | Continuty Bill embeds EU legislation in Scots law, establishes independent fully functioning watchdog & sets nature targets | FFSN Campaign
Respond to Permitted Development Review | Mar - May |  | Hilltracks |  | Government commits to removing PDRs from agricultural tracks plus carbon intensive developments. Covid delayed | Planning
Promote and seek to strengthen Land Use Strategy as mechanism to drive better integrated land use and to maximise ecosystem service benefits | Refresh of LUS due March 2021 |  | Land use |  | refreshed LUS is central to future land use support regime, which has public goods-focused basis for future SG policy and support, with particular emphasis on tackling climate change and biodiversity emergencies | F&F; Wildlife | Community Land Scotland, Scottish Land Commission, Nature Friendly Farming Network, SLE, NFUS, Confor
Ensure environmental interests adequately reflected in Regional Land Use Frameworks, with effective RLUPs in place to deliver them | From March 2020 |  | Land use |  | RLUFs effective tools for securing more environmentally sustainable and beneficial land use | F&F; Governance; Wildlife | SLC; RLUPs
Ensure environmental goals are adequately reflected in future land reform agenda and proposals, including evolution of Rights and Responsibilities statement | R&R refresh is due 2022, but updates to code of practice are expected before this - timescale uncertain. Lnd Reform input via manifestos |  | Land use |  |  | Governance | SLC
Develop Ocean recovery plan to fit with FFSN advocacy on Environment Act and LINK manifesto asks plus promoted through Scottish Fisheries Act |  |  | Marine |  | Marine targets on HPMAs/30% non-extractive; inshore management reducing impact of mobile gear & favourable (recovering) stock assessments in place | Governance | FFM
Secure well-managed inshore MPAs (phase 2) and protection for PMFs outside MPAs; well-managed offshore MPAs; well-managed deep-sea marine reserve |  |  | Marine |  | Ecosystem recovering occurring within MPAs; Productivity of fish stocks inside and outside MPAs increasing |  | WWF; FMAC members; ELUK
Secure strong ecosystem-based National Marine Plan with strong regional plans in Shetland, Clyde & other areas | Revised Marine Atlas, end 2020; Updated NMP, TBC; Regional plans TBC / summer 2020 |  | Marine |  | Marine planning to integrate fisheries management properly
Respond to Future of Fisheries Management consultation when it goes live | Easter 2020 |  | Marine |  | Aim: fisheries managed within environmental limits
Influence & respond to NPF4 call for ideas & consultation | Call for ideas: Feb 20; consultation 30 Apr |  | Planning | Response done. | National Developments include NEN, National Parks & no climate damaging developments & takes account of cumulative impacts; National performance framework & SDGs; Just Transistion. Delivery mechanisms and inclusion mechanisms. NPF4 put back until 2022. | Land use; wildlife; F&F; woodland
Advocate linking NPF4 Local Development Plans integrate Local Govt Plans and RLUPs |  |  | Planning |  | Spatial plans are integrated to deliver vision of LUS and funded approproriately | Land use
Advocate for post Aichii agenda: match IUCN 30x30 target. UK signed up to spatial targets. | May - Mar 21 |  | Wildlife |  | Scotland/UK sign up to IUCN 30% resolution; HPMAs designated | Marine
Publish briefing to use to promote nature based solutions to climate change, pest control, pollution reduction – that provide resilience to nature as well as contributing towards climate change mitigation and adaptation. | June |  | Wildlife |  | Briefing on nature based solutions & nature networks quoted & used in advcoacy to achieve transformative change in Scotland’s approach to nature and landscape conservation |  | SCCS
Promote NEN via briefing & film | By May |  | Wildlife | Briefing published June. Film launch due Sept | NEN is central to govt land use & planning policy thr NPF4 & RLUPs; delivered via govt agencies & prioritised by funders | Land use, planning | SNH; FS; NLHF
Maintain scrutiny of Aichii reporting; Edinburgh Declaration & CoP15 proposals to build strong nature targets in Scotland | March - Oct |  |  |  | Commitment to nature targets that are deliverable, measured & a key consideration in funding, planning & land use | F&F, planning, land use
Hold Scottish Government to account over the delivery of the new Scottish Forestry Strategy | Ongoing |  |  |  | The next review of the SFS resulting in changes/improvements to the strategy itself |  | FPG
Lobby for UKFS to require a higher standard of environmental outcome from all forestry | Late 2020 |  |  |  | A more environmentally focused UKFS by 2022 |  | Wales LINK; RSPB & WT nationally; Forest Policy Group
Promote an evidence-based balance between natural regen / new native woodland / commercial non-native plantations and react to examples of the failure to achieve it. |  |  | Woodland |  | Changes to pratice and policy; a balance in the numbers of new trees planted/regenerated each year; a wider understanding of the value of native woods and regen. |  | FPG; NDWG; Forest Research
Strategic objective 2: a strong voice
Apply 5 tests for a green recovery to govt policies and procedures as announced and encourage others to do same | May - Dec |  | Green Recovery |  | Polciies meet tests; those that don't are shelved; others adopt and use the tests
Ensure deer management advocacy is included in wider LINK advocacy through other Groups |  |  | Deer |  |  | Wildilfe; climate; woodland
Publish DPF funded report on progress (or lack of) in terms of deer densities and impacts on climate emissions and habitat restoration targets. | 2020-01-13 |  | Deer |  | Good media coverage
Respond to, & coordinate, Circular Coalition responses to CE Bill consultation | Nov-Dec Consultation period. |  | Economic |  | CE Bill introduced that works towards LINK ambitions, though Bill pulled. |  | Circular Scotland coalition
Change the narrative to enable move towards necessary action to meet climate and nature emergencies: making the case for ecological restoration multiple wins across sectors | March - April |  | Food and Farming |  | Land management in food & farming sector is supported to deliver ecological coherence & penalised for damaging it | Land use; wildlife | FFPFPG; Farming 1.5
Develop LINK positions and recommendations on Whole Farm Plans, agroforestry, nitrogen balance sheet and agriculture's response to climate change. | through 2020 |  | Food and Farming |  | LINK positions used by stakeholders, SG and MSPs to build better land use contributing to LINK stratetgic objectives. | Land use, woodland | FFPFPG; MSP Species Champs; SLE, NFUS
Update 2017 LINK report 'Future of Farming and Rural Land Use in Scotland' to include proposals for a new post-2024 agricultural subsidy sytem. | May/June 2020 |  | Food and Farming | updated briefing due for publication Aug | Paper used to brief SG officials and MSPs about our vision for a new subsidy system that values environmental outcomes | Species Champions | Nature friendly Farming Network
Env strategy: letter post 25 feb roundtable plus ongoing advocacy on progress and results | end Feb |  | Governance |  | Cab Sec adopts appropriate vision and outcomes with targets for strategy |  | Cab Sec Env
Scope Env Strategy targets: commission consultant report with policy focus on targets and need for them; needs and gaps. Use as basis for LINK workshop. | May for use in Autumn |  | Governance | SH due to report end Aug | Evidence base for targets underpins LINK advocacy | Wildlife
FFSN creates political space for MSPs to deliver 3 campaign asks through social media, website & media | Jan - Dec |  | Governance |  | Right to clean and healthy environment embedded in law | FFSN Campaign
Produce & use an internal LINK manifesto for Holyrood 2021 election with public version for party officials & glossy summary | Ready for Sept 2020 (parties); Jan 21 (Glossy) |  | Governance | Full draft due by Sept | Party manifestos commit to sustainable , green & socially just future | All Groups
Budget 2021: LINK ideas for budget asks in Aug / Sept ideallly using detailed costings for specific asks | draft expected Dec 2020 for agreement by mid feb 2021 |  | Governance |  | Budget supports all activities required to deliver env priorities identified by LINK | All Groups
Indy ref 2: watching brief, sharing intelligence & plan of action | Unknown |  | Governance |  | LINK Plan of action agreed
Monitor Parliamentary review of Lobbying Act and advise MSPs when required | Until spring 2021 |  | Governance |  | LINK's concerns, aligned with SCVO, on lobbying register are included in review. |  | SCVO
ERCS established | Jan - Dec |  | Legal Strategy |  | ERCS launches early 2021 with resources & work plan to meet established need | ERCS staff team
Ensure the integration of landscape interests and objectives, as articulated in the European Landscape Convention, into LINK's wider agenda for better integrated and environmentally beneficial land use | Holyrood launch Nov 2020? |  | Land use |  | Landscape is integral to wider LINK advocacy where appropriate | Governance; Wildlife; Woodland | Scottish Landscape Alliance
Sea Scotland 2020 conference on how ocean recovery can help meet SDGs | postponed to 2021 |  | Marine | Postponed to June 2021 | Profile of oceans raised and Scottish Government encouraged to set leading international standards for achieving SDGs; Cost recovery expectations met |  | SS20 Steering group partners
Plan action for Brexit CFP? | Unknown |  | Marine |  | Fisheries connected to Good Food agenda and Good Food Nation bill | Govrenance; F&F
Produce briefing: significance of land use and value for public interest and environment including role of community right to buy; after BES pie & pint night on same topic | Not urgent |  | Planning |  | National conversation started and public awareness increased on public interest of land use and land value | BES; F&F; Land use
Coordinate & deliver advocacy on funding: public funding, NLHF and trust funding; EU LIFE | ongoing |  | SEFF |  | Funding keeps pace with nature emergency rhetoric | Governance group; Wildlife Group
Biodiversity 2030 vision: 10 steps for next 12 - 18 months & FFSN nature targets | April |  | Wildlife |  | Scotland leads on strong nature targets | FFSN; WWF, SWT, RSPB
Continue to ensure MSP Champions use every opportunity to promote species and habitat nature based solutions to cc through site visits, motions | ongoing |  | Wildlife |  | Species Champions bring focus on ecological needs to all legislation | SC Coordinator | MSP Species Champions
continue engagement in Animla & Wildlfie Bill at all stages through SP incl. supporting/lobbying ECCLR MSPs who are sympathetic to submit amendments | Bill completed June |  | Wildlife crime |  |  |  | ECCLR
Produce a strategic vision for the future of woods and trees across Scotland (similar to the Food and Farming group's one) | Summer 2020 |  | Woodland |  | https://www.scotlink.org/publication/tree-and-woodland-expansion-principles-for-scotland/ | Land Group; Land Use; Food & Farming | FPG; the cultural heritage sector
Strategic objective 3: an effective network
Complete horizon scanning exercises to inform work planning and resources to maximise impact | April; August; Oct |  | Board |  |  | Staff; Hon Fellows
Maintain and build capacity in LINK Groups though dedicated member involvement | Jan - Dec |  | Groups
Contribute to funding bids and funder progress reports as required | Jan - Dec |  | Group convenors
Maintain and build staff capacity to support LINK Groups | ongoing |  | Staff
ERCS established as independent SCIO with Board and staff team | 10 July as SCIO; Jan 21 public launch |  | Legal Strategy |  | ERCS attained SCIO status 10 July. Public launch due Jan 2021 | Staff
Secure funding for next phase of Save Scottish Seas | secured to May 21; beyond 2021 ongoing |  | Marine |  | Sea Scotland secured future | LINK staff
Build profile for environment funding through partnerships and sharable comms, eg films | ongoing |  | Staff |  | This is Scotland film complete; Nature networks film, SSS film in prep | SEFF; Board | EFN; LINK funders
Work with other networks to build profile for environment within well being agenda, to be in strong position to contribute to narrative in 2021 | ongoing |  | Staff |  |  |  | SDG network & Govt team; EEB; IUCN; SCVO
Coordinate communications across the network and use LINK comms to amplify member messages and LINK priorities | Jul - Dec |  | Staff |  |  | Comms; Board; Hon Fellows
Coordinate network input to Nature & Climate CoPs | Sept - Dec |  | Staff team |  |  |  | SSCS; members
Provide workshop space for members to explore agreed priorities and identify actions | Jan - Dec |  | Staff |  | now avibale via zoom; see events programme | Groups
Agree campaign topics, remit, timescales and outcomes and put in place resources to support delivery | Sept - Dec |  | Staff |  |  | All Groups; Board
Provide regular updates to ensure LINK members have access to up to date information relating to all LINK priorities and areas of interest | monthly; fortnightly |  | Staff |  | monthly e bulletins; fortnightly member CEO updates | Convenors
Identify and use events to raise awareness, make the case for change and influence direction on key issues | Jan - Dec |  | Staff |  | See events programme | Groups; Board; Hon Fellows
Retain members, and extend network membership to stengthen capacity and reach into key audiences | ongoing |  | Staff |  |  | Groups; Board; Hon Fellows
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target. Or not started.
AMBER: on schedule but not yet complete
PINK: on schedule but has no definite end point
GREEN: achieved
YELLOW: action delayed owing to Covid-19 impact

## new
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: