## Master 2020 work plan
Activity / tasks | Timetable | Performance target (KPI) | Group leadership | Progress assessment | Outcome | Other relevant LINK Groups | Partners to work with
Strategic objective 1: Sustainable Scotland
Use SG Deer report & LINK Deer report to embed apppropriate deer management policy into govt agency action and legislation | March - April |  | Deer |  | Govt agencies remove fencing and increase culling; culling targets to halt env degradation & increase regeneration are legally binding | Land use | FLS, FS, ECLR
Engage with coalition members and MSPs on amendments to CE Bill | March - April |  | Economic |  | A CE Bill with targets and in line with LINK asks. Bill withdrawn due to Covid. |  | Circular Scotland coalition; MSPs
Work with SG to transpose / integrate better waste regulations through amended EU Waste Directive, single use plastic Directive & food waste | March - June |  | Economic |  | increase in re-use measures and full implementation of Directives | Marine
Agriculture (Retained EU Law and Data) (Scotland) Bill. | Jan-Nov 2020 |  | Food and Farming | Stage 3 to come. Objectives so far not achieved | Amendments to insert a purpose clause into Bill and commitment to non-regression included in final legislation. |  | NFUS, SLE
Good Food Nation Bill & broader agenda: to halt environmental impact of food production and consumption including fish & shellfish | expected April |  | Food and Farming |  | LINK policies recommended by committee and amendents adopted. GFN Bill withdrawn due to Covid | Aquaculture Group | Scottish Food Coalition
Contribute to Agricultural Transformation Programme for farming and food production thorugh LINK position on how the Transformation Programme should be spent | April onwards |  | Food and Farming |  | MSPs aware of LINK asks and push for incorporation during Climate Plan scrutiny. | Land Use group
Respond to second tranche of conversion funding | Autumn 2020 |  | Food and Farming |  | Ministers use funding to promote good environmental outcomes, eg support Rural Land Use Partnerships | Land use group | SLC
Work with SG for strong Continuity Bill. Work up amendments on strength of duty on principles, independence, power & function of watchdog, legal underpinning of strategy & retention of targets | March - Nov |  | Governance |  | Continuty Bill embeds EU legislation in Scots law, establishes independent fully functioning watchdog & sets nature targets | FFSN Campaign
Respond to Permitted Development Review | Mar - May |  | Hilltracks |  | Government commits to removing PDRs from agricultural tracks plus carbon intensive developments. Covid delayed | Planning
Promote and seek to strengthen Land Use Strategy as mechanism to drive better integrated land use and to maximise ecosystem service benefits | Refresh of LUS due March 2021 |  | Land use |  | refreshed LUS is central to future land use support regime, which has public goods-focused basis for future SG policy and support, with particular emphasis on tackling climate change and biodiversity emergencies | F&F; Wildlife | Community Land Scotland, Scottish Land Commission, Nature Friendly Farming Network, SLE, NFUS, Confor
Ensure environmental interests adequately reflected in Regional Land Use Frameworks, with effective RLUPs in place to deliver them | From March 2020 |  | Land use |  | RLUFs effective tools for securing more environmentally sustainable and beneficial land use | F&F; Governance; Wildlife | SLC; RLUPs
Ensure environmental goals are adequately reflected in future land reform agenda and proposals, including evolution of Rights and Responsibilities statement | R&R refresh is due 2022, but updates to code of practice are expected before this - timescale uncertain. Lnd Reform input via manifestos |  | Land use |  |  | Governance | SLC
Develop Ocean recovery plan to fit with FFSN advocacy on Environment Act and LINK manifesto asks plus promoted through Scottish Fisheries Act |  |  | Marine |  | Marine targets on HPMAs/30% non-extractive; inshore management reducing impact of mobile gear & favourable (recovering) stock assessments in place | Governance | FFM
Secure well-managed inshore MPAs (phase 2) and protection for PMFs outside MPAs; well-managed offshore MPAs; well-managed deep-sea marine reserve |  |  | Marine |  | Ecosystem recovering occurring within MPAs; Productivity of fish stocks inside and outside MPAs increasing |  | WWF; FMAC members; ELUK
Secure strong ecosystem-based National Marine Plan with strong regional plans in Shetland, Clyde & other areas | Revised Marine Atlas, end 2020; Updated NMP, TBC; Regional plans TBC / summer 2020 |  | Marine |  | Marine planning to integrate fisheries management properly
Respond to Future of Fisheries Management consultation when it goes live | Easter 2020 |  | Marine |  | Aim: fisheries managed within environmental limits
Influence & respond to NPF4 call for ideas & consultation | Call for ideas: Feb 20; consultation 30 Apr |  | Planning | Response done. | National Developments include NEN, National Parks & no climate damaging developments & takes account of cumulative impacts; National performance framework & SDGs; Just Transistion. Delivery mechanisms and inclusion mechanisms. NPF4 put back until 2022. | Land use; wildlife; F&F; woodland
Advocate linking NPF4 Local Development Plans integrate Local Govt Plans and RLUPs |  |  | Planning |  | Spatial plans are integrated to deliver vision of LUS and funded approproriately | Land use
Advocate for post Aichii agenda: match IUCN 30x30 target. UK signed up to spatial targets. | May - Mar 21 |  | Wildlife |  | Scotland/UK sign up to IUCN 30% resolution; HPMAs designated | Marine
Publish briefing to use to promote nature based solutions to climate change, pest control, pollution reduction – that provide resilience to nature as well as contributing towards climate change mitigation and adaptation. | June |  | Wildlife |  | Briefing on nature based solutions & nature networks quoted & used in advcoacy to achieve transformative change in Scotland’s approach to nature and landscape conservation |  | SCCS
Promote NEN via briefing & film | By May |  | Wildlife | Briefing published June. Film launch due Sept | NEN is central to govt land use & planning policy thr NPF4 & RLUPs; delivered via govt agencies & prioritised by funders | Land use, planning | SNH; FS; NLHF
Maintain scrutiny of Aichii reporting; Edinburgh Declaration & CoP15 proposals to build strong nature targets in Scotland | March - Oct |  |  |  | Commitment to nature targets that are deliverable, measured & a key consideration in funding, planning & land use | F&F, planning, land use
Hold Scottish Government to account over the delivery of the new Scottish Forestry Strategy | Ongoing |  |  |  | The next review of the SFS resulting in changes/improvements to the strategy itself |  | FPG
Lobby for UKFS to require a higher standard of environmental outcome from all forestry | Late 2020 |  |  |  | A more environmentally focused UKFS by 2022 |  | Wales LINK; RSPB & WT nationally; Forest Policy Group
Promote an evidence-based balance between natural regen / new native woodland / commercial non-native plantations and react to examples of the failure to achieve it. |  |  | Woodland |  | Changes to pratice and policy; a balance in the numbers of new trees planted/regenerated each year; a wider understanding of the value of native woods and regen. |  | FPG; NDWG; Forest Research
Strategic objective 2: a strong voice
Apply 5 tests for a green recovery to govt policies and procedures as announced and encourage others to do same | May - Dec |  | Green Recovery |  | Polciies meet tests; those that don't are shelved; others adopt and use the tests
Ensure deer management advocacy is included in wider LINK advocacy through other Groups |  |  | Deer |  |  | Wildilfe; climate; woodland
Publish DPF funded report on progress (or lack of) in terms of deer densities and impacts on climate emissions and habitat restoration targets. | 2020-01-13 |  | Deer |  | Good media coverage
Respond to, & coordinate, Circular Coalition responses to CE Bill consultation | Nov-Dec Consultation period. |  | Economic |  | CE Bill introduced that works towards LINK ambitions, though Bill pulled. |  | Circular Scotland coalition
Change the narrative to enable move towards necessary action to meet climate and nature emergencies: making the case for ecological restoration multiple wins across sectors | March - April |  | Food and Farming |  | Land management in food & farming sector is supported to deliver ecological coherence & penalised for damaging it | Land use; wildlife | FFPFPG; Farming 1.5
Develop LINK positions and recommendations on Whole Farm Plans, agroforestry, nitrogen balance sheet and agriculture's response to climate change. | through 2020 |  | Food and Farming |  | LINK positions used by stakeholders, SG and MSPs to build better land use contributing to LINK stratetgic objectives. | Land use, woodland | FFPFPG; MSP Species Champs; SLE, NFUS
Update 2017 LINK report 'Future of Farming and Rural Land Use in Scotland' to include proposals for a new post-2024 agricultural subsidy sytem. | May/June 2020 |  | Food and Farming | updated briefing due for publication Aug | Paper used to brief SG officials and MSPs about our vision for a new subsidy system that values environmental outcomes | Species Champions | Nature friendly Farming Network
Env strategy: letter post 25 feb roundtable plus ongoing advocacy on progress and results | end Feb |  | Governance |  | Cab Sec adopts appropriate vision and outcomes with targets for strategy |  | Cab Sec Env
Scope Env Strategy targets: commission consultant report with policy focus on targets and need for them; needs and gaps. Use as basis for LINK workshop. | May for use in Autumn |  | Governance | SH due to report end Aug | Evidence base for targets underpins LINK advocacy | Wildlife
FFSN creates political space for MSPs to deliver 3 campaign asks through social media, website & media | Jan - Dec |  | Governance |  | Right to clean and healthy environment embedded in law | FFSN Campaign
Produce & use an internal LINK manifesto for Holyrood 2021 election with public version for party officials & glossy summary | Ready for Sept 2020 (parties); Jan 21 (Glossy) |  | Governance | Full draft due by Sept | Party manifestos commit to sustainable , green & socially just future | All Groups
Budget 2021: LINK ideas for budget asks in Aug / Sept ideallly using detailed costings for specific asks | draft expected Dec 2020 for agreement by mid feb 2021 |  | Governance |  | Budget supports all activities required to deliver env priorities identified by LINK | All Groups
Indy ref 2: watching brief, sharing intelligence & plan of action | Unknown |  | Governance |  | LINK Plan of action agreed
Monitor Parliamentary review of Lobbying Act and advise MSPs when required | Until spring 2021 |  | Governance |  | LINK's concerns, aligned with SCVO, on lobbying register are included in review. |  | SCVO
ERCS established | Jan - Dec |  | Legal Strategy |  | ERCS launches early 2021 with resources & work plan to meet established need | ERCS staff team
Ensure the integration of landscape interests and objectives, as articulated in the European Landscape Convention, into LINK's wider agenda for better integrated and environmentally beneficial land use | Holyrood launch Nov 2020? |  | Land use |  | Landscape is integral to wider LINK advocacy where appropriate | Governance; Wildlife; Woodland | Scottish Landscape Alliance
Sea Scotland 2020 conference on how ocean recovery can help meet SDGs | postponed to 2021 |  | Marine | Postponed to June 2021 | Profile of oceans raised and Scottish Government encouraged to set leading international standards for achieving SDGs; Cost recovery expectations met |  | SS20 Steering group partners
Plan action for Brexit CFP? | Unknown |  | Marine |  | Fisheries connected to Good Food agenda and Good Food Nation bill | Govrenance; F&F
Produce briefing: significance of land use and value for public interest and environment including role of community right to buy; after BES pie & pint night on same topic | Not urgent |  | Planning |  | National conversation started and public awareness increased on public interest of land use and land value | BES; F&F; Land use
Coordinate & deliver advocacy on funding: public funding, NLHF and trust funding; EU LIFE | ongoing |  | SEFF |  | Funding keeps pace with nature emergency rhetoric | Governance group; Wildlife Group
Biodiversity 2030 vision: 10 steps for next 12 - 18 months & FFSN nature targets | April |  | Wildlife |  | Scotland leads on strong nature targets | FFSN; WWF, SWT, RSPB
Continue to ensure MSP Champions use every opportunity to promote species and habitat nature based solutions to cc through site visits, motions | ongoing |  | Wildlife |  | Species Champions bring focus on ecological needs to all legislation | SC Coordinator | MSP Species Champions
continue engagement in Animla & Wildlfie Bill at all stages through SP incl. supporting/lobbying ECCLR MSPs who are sympathetic to submit amendments | Bill completed June |  | Wildlife crime |  |  |  | ECCLR
Produce a strategic vision for the future of woods and trees across Scotland (similar to the Food and Farming group's one) | Summer 2020 |  | Woodland |  | https://www.scotlink.org/publication/tree-and-woodland-expansion-principles-for-scotland/ | Land Group; Land Use; Food & Farming | FPG; the cultural heritage sector
Strategic objective 3: an effective network
Complete horizon scanning exercises to inform work planning and resources to maximise impact | April; August; Oct |  | Board |  |  | Staff; Hon Fellows
Maintain and build capacity in LINK Groups though dedicated member involvement | Jan - Dec |  | Groups
Contribute to funding bids and funder progress reports as required | Jan - Dec |  | Group convenors
Maintain and build staff capacity to support LINK Groups | ongoing |  | Staff
ERCS established as independent SCIO with Board and staff team | 10 July as SCIO; Jan 21 public launch |  | Legal Strategy |  | ERCS attained SCIO status 10 July. Public launch due Jan 2021 | Staff
Secure funding for next phase of Save Scottish Seas | secured to May 21; beyond 2021 ongoing |  | Marine |  | Sea Scotland secured future | LINK staff
Build profile for environment funding through partnerships and sharable comms, eg films | ongoing |  | Staff |  | This is Scotland film complete; Nature networks film, SSS film in prep | SEFF; Board | EFN; LINK funders
Work with other networks to build profile for environment within well being agenda, to be in strong position to contribute to narrative in 2021 | ongoing |  | Staff |  |  |  | SDG network & Govt team; EEB; IUCN; SCVO
Coordinate communications across the network and use LINK comms to amplify member messages and LINK priorities | Jul - Dec |  | Staff |  |  | Comms; Board; Hon Fellows
Coordinate network input to Nature & Climate CoPs | Sept - Dec |  | Staff team |  |  |  | SSCS; members
Provide workshop space for members to explore agreed priorities and identify actions | Jan - Dec |  | Staff |  | now avibale via zoom; see events programme | Groups
Agree campaign topics, remit, timescales and outcomes and put in place resources to support delivery | Sept - Dec |  | Staff |  |  | All Groups; Board
Provide regular updates to ensure LINK members have access to up to date information relating to all LINK priorities and areas of interest | monthly; fortnightly |  | Staff |  | monthly e bulletins; fortnightly member CEO updates | Convenors
Identify and use events to raise awareness, make the case for change and influence direction on key issues | Jan - Dec |  | Staff |  | See events programme | Groups; Board; Hon Fellows
Retain members, and extend network membership to stengthen capacity and reach into key audiences | ongoing |  | Staff |  |  | Groups; Board; Hon Fellows
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target. Or not started.
AMBER: on schedule but not yet complete
PINK: on schedule but has no definite end point
GREEN: achieved
YELLOW: action delayed owing to Covid-19 impact

## Wildlife crime
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Wildlife crime penalties effectively deter and limit crime to near zero levels
Convenor:Liz Ferrell BCT; vice convenor: TBC
Animal and wildlife bill:
continue engagement at all stages through SP incl. supporting/lobbying ECCLR MSPs who are sympathetic to submit amendments | [6 empty] | ECCLR
Werritty Review:
Respond as part of wider LINK response | 2020-01-01 |  |  |  | Werrity recommendations implemented in full | with Hill tracks group & Land use group
LINK response to Wildlife Crime Report:
LINK can review published version. | [6 empty] | RSPB & PAWS Science Group
Budget bill:
Contribute to wider LINK response: highlighting issue of wildlife crime funding; also with Brexit, loss of LIFE funding [?] | 2020-02-01 |  |  |  | Crime reporting is regular and comprehensive producing realistic reporting data | Governance Group
Other
Review of natural Injustice report. | WHEN | [5 empty] | Onekind campaign
Another roundtable event on review of Natural Injustice | DO YOU HAVE TIME & CAPACITY
Complete actions from wildlife crime parli event Oct 19: WHAT ARE THEY?
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Wildlife (2)
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Linking biodiversity and climate change agendas through nature-based solutions. Biodiversity and nature recovery is funded
Convenor: Craig Macadam; vice convenor: Paul Walton. Dilraj, Advocacy Officer; Juliet Sp Champ coord
Nature based solutions
Promoting nature based solutions to climate change, pest control, pollution reduction – that provide resilience to nature as well as contributing towards climate change mitigation and adaptation. |  |  |  |  | Ecosystems are protected, enhanced and restored. This requires a transformative change in Scotland’s approach to nature and landscape conservation | Separate working group on climate action plan update? | SCCS
12 point plan for biodiversity cf climate plan | 2020-01-01 |  |  |  |  | WWF; RSPB
Produce NEN briefing note, NEN visual resource/information sheet: | January 2020 |  |  |  | NEN in NPF4 |  | Scottish Infrastructure Strategy?
NEN is the Strategic spatial framework for nature recovery
Produce NEN film for launch | by September 2020 |  |  |  | RLUPs to deliver NEN as spatial framework for nature recovery | Land Use group work on RLUPs
Aichi Reporting & beyond Aichii
Comment on Scottish Government Aichi target update through Scotsman; RSPB, SWT, Plantlife plus others | due in April 2020 |  | Isobel to coordinate? |  |  | Funding sub gourp, marine
Comment on Edinburgh declaration: before publication likely to be light touch. LINK Thinks blog as comment after 3 April |  |  | PW. Dl before 16 March. |  |  | Sheila, WWF, SWT
In depth comment / action to respond to edinburgh declaration | 22 May: Int Biodiveristy day
Contribute / comment on future biodiversity targets by identifying gaps and highlighting practical actions for delivery in Scotland | as needs basis |  | PW
SBS 2030 Challenge Action Plan
Ensure nature based solutions to cc is delivreed thorugh nature rich language and lobby whenever possible to ensure ecological sense | Feb - March |  | PW thorugh coordination specsi gourp 9plus craig)
Asses whether to comment on SG report to Parli on SBS progress: find out where this is | due to Cab Sec on 23 jan |  | DL/ VT to find out timing
Influence 2030 action challenge plan through SBS Project 3
Biodiversity 2030 vision: 10 steps for next 12 - 18 months. Draft for sign up by wider LINK w/b 24 feb | Feb. Due for launch 30 march |  | Isobel |  |  | WWFS, RSPB, SWT
Promote Peatland recovery work as nature based solution through IUCN World Congress, Marseille: UK Peatland event plus RBGE showcase 31 March event talk | [6 empty] | UK peatland Committee
Nature recovery targets within the FFSN campaign:
Esnure FFSN nature target ask makes sense for WG | March - April |  |  |  |  | FFSN
Species Champions:
Continue to ensure MSP Champions use every opportunity to promote species and habitat nature based solutions to cc through site visits, motions | ongoing |  | Juliet to maintain close and coordinated MSP Champion relationships. |  | Species champions: climate impacts on species and how Nature based solutions can help |  | MSP Species champions
Funding
Advocacy on public funding | [5 empty] | Funding advocacy Group
Replacing LIFE etc
Trust funding
4th prioirty
Vitalise group by agreeing more capacity |  |  | need to find convenor
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Planning (2)
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Good places for people and wildlife achieved through plan led Planning system |  |  |  |  | Convenor: Clare Symonds
Influence the National Planning Framework 4 so it delivers for climate and nature:
early engagement in NPF4 process:call for ideas. Member bodies will also respond. | 2020-03-31 |  | Clare, following meeting with Simon Bonsall and Eric Dawson |  | rural housing, affordable & energy efficient housing, green belt, behavioural change, climate, land value tax, incorporation of SPP are all included. Measured against delivery against climate and nature targets and reproted to parliament. |  | Members to analyse others responses (published July 2020) to look for crossovers.
NPF consultation opens Sept 2021 to be laid before Parl Autumn 2022: lasts for 10 years and in context of climate and nature crises | 20/09/2021 for 120 days |  |  |  | National Developments include NEN, National Parks & no climate damaging developments & takes account of cumulative impacts; National performance framework & SDGs; Just Transition. Delivery mechanisms and inclusion mechanisms. | Wildlife group, Land use, food and farming, woodland groups. Send out for wider LINK sign up. |  | NPF Bill reaches Parliament after May 2022
LINK workshop: agree vsion for delivery thourgh NPF4. Result will be response to Call for Ideas consultation. | 12 March. Repurpose Land group meeting |  |  |  | NPF4 meets net zero and nature targets | Wildlife group, Land use, food and farming, marine woodland groups. No sign up due to Covid 19 furloughs. |  | Work with Wildlife Group to define NEN for NPF4
Govt interim statement on NPF 4 expected Autumn 2020 | 2020-09-01 |  | Clare Vhairi liaise on MSP correspondence |  |  |  | Liaise with MSPs in run up to interim statement
Produce NPF4 LINK briefing, using the climate and nature emergency and green recovery lens – for May 2021 targetted at new MSP intake. | After October 2021 |  |  |  | Informs LINK and wider external organisations responses to NPF4 consultation
2050 Climate group workshop: PD
Secondary legislation and planning guidance: HOW?
Possible campaign around NPF4: LINK input (briefing) to NPF4 tied to key moments to mobilise wider engagement. | March: Launch e action call for support to govt for LINK NPF4 ideas. Sept: follow up in sept with call for individual submission to consultation. Process put forward by 1 year due to Covid. |  |  |  | LINK ideas are included in NPF4 consultation and widely supported | Closer engagement with Land Use, Reform and Economics groups |  | e action will encourage individuals to respond using LINK ideas written up
LINK reprs to attend NPF4 Scot Gov roadshows & encourage members to attend. Encourage other networks to do same. | roadshows completed. |  |  |  | Increase engagement at public and community level; plant the seeds of issues needing to be covered by NPF4
Land Use Strategy & RLUPs
LUS RLU Plan delivery through NPF4: work with Land use Group to work out how to deliver LINK land use vision through NPF4 | define with land use group |  | catch up call between convenors and CO July 2020 |  |  | Work with Land use Group on RLUPs and LUS Local Place Plans | Scottish land commission
Advocate linking NPF4 Local Development Plans integrate Local Govt Plans and RLUPs |  |  |  | Spatial plans are integrated to deliver vision of LUS and funded approproriately
LINK NPF presentation to citizen assembly
Govt’s work programme commitment to implement the Planning Act
seek an early 2020 meeting to discuss SG plans and influence them: Simon and Eric. Pre meeting to agree lines | 2020-02-21 |  | Clare |  | Set tone for and identify level of detail / strategic vision required in LINK response | Wildlife, Land use, Marine (Charlie), Economics
LINK reps keep an eye on stakeholder groups - Development and Planning, Community Engagement as identified in SGovt work programme: maintaining watching brief, alert Planning group and input LINK view if appropriate | 2020 - 2022 |  | Diarmid; Charlie, Clare (x2) |  | LINK input on relevent issues is received by SG |  |  | add in lnk
Permitted Development Rights review:
Respond to the Permitted Development Rights review consultation. | 28/01/2020 Delayed due to Covid, timescale uncertain |  |  |  | SPP includes Link asks
LINK position on PDR developed | 2020-01-28 |  |  |  | Carbon intentsive developments with PDR are remved. Also hill tracks | Hilltracks: work with PDR team
Respond to next stages once known
Land value & economy project: REALISTIC? | Not urgent
Seminar for academics, MSPs, NGOs | Not urgent |  |  |  | BES Pie and Pint night: ask maggie
Briefing: significance of land use and value for public interest and environment including role of community right to buy | After pie and pint night |  |  |  | National conversation started and public awareness increased on public interest of land use and land value | Work with FF Groups on land use and public interest def
Desirables
Monitoring impact of development on wildlife – baseline produced HOW and WHO? | [5 empty] | Work with Wildlife Group on baseline (if agreed)
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Marine
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Our seas: are home to ecologically productive habitats and wild seascapes with sustainable fish & marine stocks and flourishing coastal communities
| From January 2020 |  | Convenor: Calum Duncan. Vice convenor: Sarah Dolman. Esther, MPEO
Develop and advocate ocean recovery narrative in Scottish marine policy, including urgent legislative commitments to recovery targets:
Ocean recovery agenda: Environment Act with Marine Targets (GES++) with FFSN (Ocean Manifesto) | FFSN workshop Jan 2020 COP15 Intercessional Manifesto soft launch - May Possible Manifesto launch event - August/September | Edinburgh Declaration' reflects LINK ambition Ocean manifesto asks are adopted by Scot Gov |  | Commitment to Environment Act/marine targets in legislation; HPMAs/30% non-extractive committed | Good Environmental Status ++ achieved | FFSN agenda link up to nature recovery targets | Sea Scotland 2020? UN Oceans Conference LINK member observers for COP Intercessional
Ocean recovery agenda: Scottish Fisheries Act (CFP++) through FFM process (Ocean Manifesto) | TBC |  |  | Large area of inshore managed to reduce impact of mobile gear (may be achieved through PMF review); Favourable stock assessments (stocks recovering) | Fisheries managed within environmental limits |  | FFM: depends what SG suggests in high level strategy
Marine Protected Areas
Advocate for post Aichii agenda: match IUCN 30x30 target. UK signed up to spatial targets. | April CoP15 intercessional |  |  | HPMAs considered for Scotland | Scotland/UK sign up to IUCN 30% resolution; HPMAs designated | Wildlife Group | ELUK;
Secure well-managed inshore MPAs (phase 2) and protection for PMFs outside MPAs | Consultation TBC | Secure a meeting with Marine Scotland as part of 'further engagement'; Scottish Government give consideration to LINK alternative proposals; Consideration of climate and biodiversity emergency reflected in consultation proposals; Scottish Government influenced by outcome of MPA poll. | Opinion poll: MPEO (with CD and SD) |  | Ecosystem recovering occurring within MPAs; Productivity of fish stocks inside and outside MPAs increasing
Secure well-managed offshore MPAs | Management proposals to be published/laid in Parliament April 2020? | Management measures are equal to or strengthened from pre-Brexit proposals; Domestic provisions for management of offshore MPAs are robust; Measures are reflective of climate and biodiversity emergency. |  |  |  |  | WWF; FMAC members; ELUK
PMF review
Secure 4 well-managed MPAs for mobile and seabed species | Responded to consultation, August 2019 Consultation outcome, Feb-Mar 2020 Management measures TBC (likely into 20201 | Consultation outcome is clearly influenced by LINK member activity (e.g. volume of campaign responses by MCS/SWT and WDC); Consultation report cites LINK consultation response; 'Recover' objective for basking shark, Risso's dolphin, minke whale and sandeel is considered by Scot Gov. |  | 4 MPAs designated with statutory management that will enable recovery of features | Designated PMFs increasing; Data gaps for data deficient species (cetaceans) being filled
Secure well-managed deep-sea marine reserve | Responded to consultation, December 2019 Consultation outcome, June 2020? Management measures TBC (likely 2021) | Consultation report cites or is influenced by LINK response |  | DSMR designated with statutory management that will enable recovery of features.
Develop thinking and advocacy around recovery of natural marine carbon sinks through legislation/policy to help mitigate climate crisis | LINK Environment Week/Reception, May 2020 Sea Scotland, June 2020 | Climate Change (Emissions Reduction) Scotland Act provision for blue carbon is applied in future MPAs and considered appropriately in new Climate Plan;
Marine Planning
Secure strong ecosystem-based National Marine Plan | Revised Marine Atlas, end 2020; Updated NMP, TBC |  |  |  | Marine planning to integrate fisheries management properly | SWT Orkney Community Voice project
Respond to draft Shetland Regional Marine Plan | Responded to consultation, December 2019; Consultation outcome TBC
Respond to draft Clyde Regional Marine Plan | Consultation expected, summer 2020 | Draft reflects LINK asks
Secure remaing Regional Marine Plans
Sea Scotland 2020 conference on how ocean recovery can help meet SDGs (8-9 June 2020) | 8 -9 June |  | MPEO, with CD and SS20 steering group members |  | Profile of oceans raised and Scottish Government encouraged to set leading international standards for achieving SDGs; Cost recovery expectations met |  | SS20 Steering group partners
ECCLR Inquiry on marine planning | First half 2020 | ECCLR report recommends greater effort to roll out RMPs |  | More funding secured for RMPs; Orkney MPP formally designated | More MPPs delegated and RMPs under development with appropriate resourcing; Marine plans fully intetrate management of fishing
Watching brief on National Islands Plan implementation
Offshore wind marine plan | [6 empty] | Member-led, LINK support as needed
Seaweed review group is precautionary in outputs
Aquaculture: inquiry follow up tracking progress against targets (?)
Fisheries
Respond to Future of Fisheries Management consultation when it goes live | circa. Easter 2020 | Presumption against trawling and dredginh across large part of inshore adopted |  |  | Aim: fisheries managed within environmental limits
UK Fisheries Bill - feeding into Scottish response to Joint Fisheries Statement
Plan action for Brexit CFP? |  |  |  |  | Fisheries connected to Good Food agenda and Good Food Nation bill
Respond to By-catch report | late 2019 – early 2020 |  |  |  | Well-managed fisheries as nature based solution to CC and ocean recovery
Fundraising
Secure funding for next phase of Save Scottish Seas (on-going) | By end may 2020 |  |  |  | MPEO post & project secured
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Land use
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | an integrated approach to LINK’s engagement with developments from the Land Reform Bill, seeking join up with the principles of the Land Use Strategy, and ensuring that landscape concerns are sufficiently recognised in decisions around land use.
Land Use Strategy
Promote and seek to strengthen Land Use Strategy as mechanism to drive better integrated land use and to maximise ecosystem service benefits | Refresh of LUS due March 2021 |  | Sub-Group (Convener: John Thomson) | Meeting to establish contact with new SG lead (Philip Whyte) scheduled for 16 April | Next iteration of LUS better reflects LINK ambitions and priorities | Land Group Wildlife SG - NEN Landscape SG | Scottish Land Commission
Ensure that refreshed LUS is central to future land use support regime | Ongoing | LUS recognised as overarching framework for rural policy | LINK collectively | Success hitherto reflected in inclusion of commitment to RLUPs and RLUFs in Programme for Government | Public goods-focused basis for future SG policy and support, with particular emphasis on tackling climate change and biodiversity emergencies | Food and farming SG Planning Group - significance and role of LUS must be reflected in NPF4
Build wider coalition of Land Use organisations including Community Land Scotland, Scottish Land Commission, Nature Friendly Farming Network, SLE, NFUS, Confor | Across 2020. Ongoing building of relationships. | More supportive and complementary input achieved | All
Regional Land use Partnerships
Ensure adequate knowledge and understanding of potential benefits of RLUPs and RLUFs across LINK network | Briefing note Jan 2020 |  | Andrew Midgley RSPB | Note issued | Improved understanding to be confirmed at May networking meeting
Influence SLC thinking and advice to SG through direct contact, consultation responses and workshop participation | Respond to initial consultation paper by 17 April Group members to meet SLC (and possibly SLE) staff |  | Sheila George WWFS | Initial discussion of line to take 12 and 23 March | SLC advice to SG (due Jane 2020) substantially in line with LINK thinking and ambitions
Ensure SG adopts environmentally beneficial elements of SLC advice | Summer/autumn 2020 | Comment on SLC advice and respond to any SG consultation | Sub-Group | Ongoing liaison with SG officials to be established (see 4 above) | Network of RLUPs set up in form reflecting LINK views |  | Sympathetic local NGOs?
Participate as appropriate in any RLUPs established | Winter 2020/21 onwards | Participate fully in any "pilot" RLUPs | Relevant LINK bodies (NB co-operation/co-ordination may be required) |  | Environmental interests adequately represented
Ensure environmental interests adequately reflected in Regional Land Use Frameworks | ?2021 onwards |  | Sub-Group at national level, relevant LINK bodies regionally and locally |  | RLUFs effective tools for securing more environmentally sustainable and beneficial land use
Land reform
Monitor and influence as necessary evolution of Rights and Responsibilities statement | Refresh is due 2022, but updates to code of practice are expected before this - timescale uncertain. | Influence codes of practice. | Landowning NGOs have particular interest in aspects affecting their operations; Sub-Group in relation to wider impacts |  | Statement and associated guidance effective in promoting more environmentally responsible land management | Relevant to many LINK groups concerned with securing better land management | SLC inviting LINK involvement
Ensure environmental goals are adequately reflected in future land reform agenda and proposals | SLC likely to feed in proposals ahead of 2021 Holyrood election | Any LINK "asks" to be incorporated in wider manifesto request | Sub-Group working in wider LINK context |  | Responsible environmental stewardship seen as key aim and integral part of overall land reform agenda | Wildife Group
Landscape policy
Ensure the integration of landscape interests and objectives, as articulated in the European Landscape Convention, into LINK's wider agenda for better integrated and environmentally beneficial land use | SLA has deferred launch of initial findings and recommendations, originally planned for April 2020. Holyrood launch may now take place in November. | SLA and LINK agendas closely aligned | John Thomson, as Chair of both SGs |  | Higher priority for landscape interests and objectives in policy and decision-making, consistent with overall LINK aims | Landscape SG | Scottish Landscape Alliance
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Governance (2)
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Scotland’s governance operates to highest environmental standards in EU
Brexit & Env Strategy
GUL and ELU: 2 way information to inform outputs on common frameworks and trade | ongoing |  | LWA, VT
Misc Brexit issues: eg internal market; no deal at end transition | ongoing |  |  |  |  | F&FG and Marine | GUK; ELUK
Env strategy: letter post 25 feb roundtable plus ongoing advocacy on progress and results | 25 feb onwards |  |  |  | appropriate vision and outcomes with targets | Funding Group
Continuity Bill amendments on strength of duty on principles, independence, power & function of watchdog, underpinning of strategy & retention of targets | March to nov |  | Bill team Group: LWA, VT, SG, Isobel, Diarmid with Thom, Lindsay & fergus input
Scope Env Strategy targets: commission consultant report with policy focus on targets and need for them; needs and gaps. Use as basis for LINK workshop. | May for use in Autumn |  | VT with consultant & psosible volunteer
Hghlight to MSPs LINK's asks in relation to amendements to Continuity Bill with ref to EU principle at each stage | March to nov |  | Bill team Group: LWA, VT, SG, Isobel, Diarmid with Thom, Lindsay & fergus input |  | All LINK amendments to Continuity Bill passed |  | Relevant MSPs
FFSN |  |  | Miriam lead with Campaign support team
Influence the delivery of three pillars of FFSN asks – principles and governance and SIs/ SSIs plus watchdog |  |  |  |  | Right to clean and healthy environment embedded in law |  | UK Envt Bill: comparison re SNP at Westminster on watchdog; targets; nature recovery network
Review campaign outputs and outcomes and agree next steps |  |  | VT, Miriam
Workhops outcome to be included in satregy : blogs from workshop |  |  | Miriam |  |  | Willdife, Marine & Land use Group input
Cross check with campaign group: agree tactics and provide policy support
ACTION FOR Envt Act to build on skeleton of Continuity Act & other FFSN asks
Env Rights
Gaps in legal Strategy group that come back to Gov Group once ERCS is established | Summer |  | LWA |  |  | ERCS
Environmental Courts: Environmental rights (Aarhus compliant) in HRs Act proposal; plus progress towards Environ Courts |  |  | MC |  | Aarhus procedural rights embedded in law | ERCS | Aarhus issues covered by Scot Gov TF (HRs)
Political parties and elections Manifestos & 2021 election:
Produce an internal LINK manifesto for Holyrood 2021 election. Version for party officials to be ready by September 2021. | March to early September |  | Vhairi, with steer from Lloyd and Gov Group |  | A manifesto which contains the detail of LINK's asks for the 2021-2026 Parliament. To be shared with members and key party officials. | All Groups | Party officials.
Meetings with party officials and MSPs to promote the contents of LINK's manifesto | September - February 2021 |  | Vhairi, with steer from Lloyd and parliamentary officers |  | LINK manifesto asks included in party manifestos |  | Parliamentary officers, party officials.
Produce a glossy, publicly accessible version of the manifesto. | 2021-01-01 |  | Vhairi, with steer from Lloyd and Gov Group |  | Public version of the manifesto, tying in with FFSN targets work. |  | Heedi for design?
Budget 2021: ideas for budget asks in Aug / Sept ideallly using detailed costings for specific asks | draft expected Dec 2020 for agreement by mid feb 2021
Party conference attendence and activities: details on Advocacy team trello board | Spring & Autumn
Annula Prog for Govt: input in summer 2021 for new Govt | 2021-09-01 |  |  |  | Agreed set of LINK ‘asks’. LINK asks are included in each manifesto
Indy ref 2
Indy ref 2: watching brief, sharing intelligence & plan of action | Unknown
Indy Ref 2 Ref Challenge 2: how to produce and tactis fro action | Unknown
Input into lobbying register review
Share LINK briefing with committee clerks and other third sector partners. | March/April |  | Lisa and Vhairi |  | LINK concerns to be backed up by other organisations (eg SCVO) and on committee agenda. |  | SCVO/SCCS/Scottish Power/Drax/Parliamentary clerks
Meet MSPs on PLPA Committee to share LINK concerns | April/May |  | Vhairi |  | MSPs to be aware of LINK's concerns with lobbying register and to include those in their review. |  | Jenny Marra MSP, Alex Neil MSP
Monitor Parliamentary review and advise MSPs when required | Until spring 2021 |  | Vhairi |  | LINK's views are raised during the course of the parliamentary review
Establishment of ERCS to address environmental justice issues:
Launch ERCS | 2021-01-01 |  | ERCS staff with Group support & shadow Board |  | Long term funding for ERCS
Set up the ERCS as an independent SCIO | 2020-10-01
Other Governance Matters issues:
Regulator assessment: assess once watchdog is in place; cross check with independence of funding | summer |  | Consultant report |  |  | Funding group |  | watchdog should assess if quangos have appropriate expertise on boards; plus have sufficient funding to deliver stat duties
Provide advice to LUG and consider & comment on governance role of RLUPS: workshop in March, propoposals with SG by summer | March and summer |  |  |  |  | Land Use Group | RLUPs another tier of govt? cg DMGs; Water AGs; Dist SBs.
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Deer
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | sustainable deer management, particularly as part of the sustainable upland land use agenda
Deer management report
Publish LINK position statement (ready) in early 2020 when SNH report and Deer Working Group reports are published. | early 2020 |  | Convenor: Duncan Orr-Ewing; vice convenor: Mike Daniels. DO support |  |  |  | SNH Deer report / Report on deer management to SG
Publish DPF funded report on progress (or lack of) in terms of deer densities and impacts on climate emissions and habitat restoration targets. | 2020-01-13 |  |  |  | Report launched and reported widely in press
Other policy hooks for deer advocacy
As well as the ECCLR committee / SG scrutiny of the report use our deer asks for a range of policy opportunities ahead: UN Convention on Biological Diversity conference in Edinburgh spring; UN Climate Summit Convention of the Parties (COP 26) in Glasgow, Aichi biodiversity targets, Forest Land Scotland new deer management policy etc.
Engage and support FLS and FS as they deploy their new deer management policies which already appear to be very helpful - less fencing and more culling; | [6 empty] | FLS, FS
Develop a strategy for advocacy for the ECCLR committee members. | [6 empty] | ECCLR
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Economics
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Scotland has halved resource use (raw materials)
Circular Economy Bill:
Coordinate and run Social media to raise awareness about the consultation and encourage responses. Direct and via coalition partners. | Nov-Dec Consultation period. |  | Phoebe to lead with advocacy, parliamentary support from LINK staff |  | A CE Bill with targets and in line with LINK asks |  | Coalition partners
blog & SM comms response to Scotland carbon footprint report published WHEN? | 2019-12-01 |  | Phoebe | Didn't happen as report came out same time as CE consultation and was missed.
Conduct public poll on attitudes | Feb - March |  | Phoebe | Stats to use in comms | Success in campaign asks
Possible roundtable event in parliament - Greens to lead. | Post consultation, pre Bill: to end March: |  | Phoebe to respond to Green's lead | Increase in MSP understanding of CE |  |  | Ecomony Committee - not currently involved in CE
MSP engagement – meetings, MSP trip to build understanding of circ econ needs? | Feb – Mar: Conduct Public poll and comms around it. |  | Phoebe | Increase in MSP understanding of CE and our asks. | Hopefully support for our asks |  | Coalition partners re trip
Plan a series of media stories on public messages to increase support for action needed on circ econ. PR placing required? | March - August | FP Funding to support short term contract to place press and media: Azra? | Phoebe with help from Azra |  | Public awareness and profile of CE |  | Coalition partners contributing blogs
Think of good people to give evidence in stage 1 of CE Bill | March April – Stage 1 of Bill |  | Phoebe, members of Economics Group | Individuals lined up who can contribute to debate | robust contributions to evidence giving sessions |  | Coalition partners
Develop amendments for - | March April – Stage 1 of Bill |  | Phoebe, members of Economics Group | amendments developed
Engage with coalition members and MSPs on amendments: | June-November -Stages 2 & 3. |  | Phoebe, members of Economics Group | Amendments put forward by MSP | Amendements accepted
Autumn 2020 budget
Other CE policy, measures & consultation priorities:
Maintain watching brief on Stage 3 of SNIB Bill |  |  |  | completed | CE included as an aim of SNIB
Respond to SG consultation on CEP (amended Waste Directives) | March - May 2020 |  | Phoebe |  | LINK response and indivual coaltion members respond |  | Coalition partners
Climate Plan - input | March - May 2020 |  | Phoebe / FoES |  | So that CE is embedded in it, beyond just Waste section
Coordinate with Coalition to respond to SGovt consultation on the best way to transpose requirements under the Single-Use Plastic Directive Before July: | April - June 2020 |  | FoES, MCS |  | LINK response and indivual coaltion members respond |  | Coalition partners
Commission research on (a) what tools make circ econ work and (b) what actions under existing powers would make shift required. DON'T THINK WE HAVE BUDGET FOR THIS NOW
Event with EEB for SGovt consultation on new legislation required to meet recent amendments to the European waste directives Some time in 2020, | 2020-05-01 |  | Phoebe |  | Feed into SG stakeholder engagment - ultimately like to see increase in re-use measures and full implementation of Directives |  | Coaltion partners, ZWS
Consider potential to respond to a consultation on building regulations through coalition
Consider potential to respond to consultation on food waste measures through coalition |  |  |  |  | Reduction on food waste. Residual waste collected and used
Circular procurement in place
Other:
In 2021 Call on SG for a new Economic Strategy. | 2021 |  | Matthew |  | 2021 Programme for Govt delivers new Economic Strategy, to deliver on FM’s concept of well-being. Or pledges in party manifestos |  | SCCS led / joint SCCS LINK
Run An event to act as an evidence session for the Just Transition Commission with SCCS or by SCCS with LINK support |  |  | Matthew / FoES |  |  | Coordinate with Wildlife & Planning groups
Respond to consultation on Scotland’s Infrastructure strategy, with green & blue infrastructure now included: expected 2020
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Food and Farming
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | Healthy soils with sustainable agricultural systems that produce supplies of safe healthy food, protect natural resources and enhance wildlife, habitats and cultural heritage, and provide jobs in rural areas, contributing to a diverse rural economy.
Influence the future of public subsidies towards environmental public goods:
Change the narrative to enable move towards necessary action to meet climate and nature emergencies: making the case for ecological restoration multiple wins across sectors | Across all strands of work. |  | Pete Ritchie (Nourish) Convenor, Scott Leatham SWT Vice-Convenor.
Key 2020 legislation for action:
Agriculture (Retained EU Law and Data) (Scotland) Bill. | Jan-Nov 2020 | Amendments to insert a purpose clause into Bill and commitment to non-regression included in final legislation. | Scott and Pete | LINK recommendations included in Stage 1 report - ACHIEVED Amendments voted into Bill at Stage 2 |  |  | NFUS, SLE
Good Food Nation Bill & broader agenda: to halt environmental impact of food production and consumption including fish & shellfish | expected April | The Bill to include an environmental perspective, reflecting LINK's views. |  | LINK policies recommended by committee and amendents adopted. |  | Aquaculture Group | Scottish Food Coalition
Post-2024 agri/rural support system | [6 empty] | FFFPG
Support FFFPG: reactive tasks as needed | until Spring 2020 |  | ALL
Contribute to Agricultural Transformation Programme for farming and food production. | Across 2020 | Details of the Programme to be outlined in updated Climate Plan. |  | Develop LINK asks for the how the Transformation Programme should be spent. Work has begun to form a position over email in April. | MSPs aware of LINK asks and push for incorporation during Climate Plan scrutiny. | Land Use group
Develop LINK positions and recommendations on Whole Farm Plans, agroforestry, nitrogen balance sheet and agriculture's response to climate change. | Across 2020 |  | ALL | Policy workshop on 1st April | LINK positions used by staekeholders, SG and MSPs to build better land use contributing to LINK stratetgic objectives. | Land Use group, woodland
Respond to second tranche of conversion funding | Autumn 2020 | Ministers to consider using funding to promote good environmental outcomes, eg support Rural Land Use Partneships | Pete | MSPs, SPADs and officials aware of asks. |  | Land use group | SLC comments on funding?
Update 2017 LINK report 'Future of Farming and Rural Land Use in Scotland' to include proposals for a new post-2024 agricultural subsidy sytem. | May/June 2020 | An updated report outlining the Group's vision for a post-CAP subsidy system. | Scott/Vicki with input from Group members | Initial plan has been drafted. Group members to sign up to draft key paragraphs | A paper that can be used to brief SG officials and MSPs about our vision for a new subsidy system that values environmental outcomes | Species Champions | Nature friendly Farming Network
UNFCCC COP26 (Glasgow)
Extend invitation to global Food and Climate Alliance (coalition of global NGOs on food sustainability - reports on food procurement at COPs) for a meeting – joint messaging, actions, general chat, around COP26 [Scott action initially, post-COP25]. | 2020-11-01 |  | Scott
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Hilltracks
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | forestry and agricultural vehicle tracks are fully integrated into the planning system.
Beryl Leatherland and Helen Todd, co-convene. RS, SWLG, NEMT, JMT, RSPB, NTS, BSCG, CC, APRS, SCNP.
PD Review consultation
Respond to Jan consultation on work programme for review of permitted development rights | end Jan |  |  |  | LINK response favourably influences forthcoming consultation on review of PDRs | LINK Planning Group
Respond to following consultation on Review of permitted development rights | March-May |  |  |  | Government commits to removing PDRs from agricultural tracks | LINK Planning and Landscape Groups | Related and strong campaigns: revive; rewilding alliance.
Engage supporter base to respond too. | March-May |  |  |  | 300+ responses from campaign supporters sent to government to demonstrate ongoing public interest | Members of the hilltracks sub group plus Mountaineering Scotland | Keep in contact with Andy Wightman MSP who campaigned previously on this topic
Have meeting with Kevin Stewart Planning Minister (requested): on PDR review process; [Note, meeting request refused, but will continue to meet/correspond with other stakeholders] | March-May |  |  |  | Gain support for change in the law, showing government wider stakeholder interest in topic. |  | MSPs, SNH, national parks
Other policy actions
Respond to Werrity report | 2020-01-01 |  |  |  |  | Land use Group, Wildlife Crime sub group
Continue to monitor and react as necessary | Ongoing |  |  |  | maintain evidence base and add more case histories
Respond to Code of Good Practice for ATV use | Timetable controlled by CNPA, will respond when appropriate |  |  |  | ATV use good practice code |  | Cairngorms NPA
Support related campaigns: revive; rewilding alliance | As opportunities arise
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## SEFF
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | To increase funding for environment to match action needed against climate and nature emergencies
Convenor: Stephen Gardner; vice convenor; Alison Connelly. DO support
Funding advocacy subgroup: Craig Macadam, Bruce Wilson, Paul Walton, Aedan Smith, Charles Dundas, Stephen Gardner, DL
Information sharing & training
Hold 4 meetings per year (March, June, Sept, Dec). speakers invited.
Funding advocacy
Trust funding, including NLHF: work with EFN & NLHF to target funding to environment | [6 empty] | EFN new Scotland post; NLHF, SNH
Maximise film impact
Public funding: follow up blog with budget advocacy | Jan - Feb 2020 |  |  |  | Decline in public investment in environment reversed | Governance group; Wildlife Group | SNH Group on funding biodiversity for 2020
briefing to influence rhetoric around budget | [5 empty] | Governance group; Wildlife Group | Scottish Greens
EU & LIFE funding: complete RSPB led work on LIFE funding; structural funds & BREXIT implications | [5 empty] | RSPB led
Aichii target 20 reporting: continue advocacy on target reporting |  |  |  |  | T20 accurately reported on biodiversity conservation funding only | Wildlife Group
Return on investments: commission research on return on investment in environment | Commission jan 2020 |  |  |  | Research reflects wider benefits of investment | Governance group
4.
5.
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Climate change
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target:
Coordinate response to Climate Change Plan | [5 empty] | Wildlife Group
Coordinate LINK input into Climate COP 26 (Glasgow) | 2020-01-14 |  |  |  |  | Member reps & LINK CO | SCCS
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## Woodland
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: | discuss issues such as tree health; forestry policy; tree protection; woodland creation funding and targeting
Convenor: Charles Dundas
Produce a strategic vision for the future of woods and trees across Scotland (similar to the Food and Farming group's one) | Summer 2020 | 1. Agree shared principles document; 2. Workshop the strategic vision; 3. Secure sign up from across members. | Arina and Alan |  | A completed and agreed document published on the LINK website | Land Group; Land Use; Food & Farming | FPG; the cultural heritage sector
Promote an evidence-based balance between natural regen / new native woodland / commercial non-native plantations and react to examples of the failure to achieve it. | Ongoing | 1. Include section on this is strategic vision; 2. Synthesis existing evidence on cultivation guidance work / RSPB Trees & Carbon research / IUCN Draft Peatland and Trees; 3. Increased area of native woodland/natural regeneration reported in annual planting stats. | Scott |  | Changes to pratice and policy; a balance in the numbers of new trees planted/regenerated each year; a wider understanding of the value of native woods and regen. |  | FPG; NDWG; Forest Research
Promote a greater diversity of innovative woodland types through highlighting success stories - including around agroforestry | Late 2020 | 1. Compile case studies; 2. Write report. | ? Possibly commissioned using DPF ? |  | Case studies
Hold Scottish Government to account over the delivery of the new Scottish Forestry Strategy | Ongoing | 1. Follow the timescale for Forest Strategy reporting and reviewing to Parliament with LINK's own programme of assessment | Alan |  | The next review of the SFS resulting in changes/improvements to the strategy itself |  | FPG
Lobby for UKFS to require a higher standard of environmental outcome from all forestry | Late 2020 |  | Arina |  | A more environmentally focused UKFS by 2022 |  | Wales LINK; RSPB & WT nationally; Forest Policy Group
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved
Progress key:
RED: behind schedule. Text idenftying what tasks to attain target
AMBER: Target on schedule but not yet complete
PINK: target on schedule but has no definite end point
GREEN: target achieved

## new
Activity / tasks | Timetable | Performance target (KPI) | Task leadership | Progress assessment | Outcome | Other relevant LINK activities | Partners to work with
Strategic headline target: